## Instructions
CI Interface Register — Template
Per [XXX-CM-PROC-001] CI Identification Process, §5.5.1 and Section 6. One row per CI-structure boundary. Maintained current in the CSA system; constitutes CM's evidence for Floor ID F35.
How to use
• Enter data only on the 'Interface Register' sheet, below the header row. Gray italic rows are examples — replace them with real data.
• Rows are boundaries, not documents: every pair of interfacing sibling CIs, every boundary between the system and an external system, and every boundary between Acquirer-controlled and Supplier-controlled levels gets a row. One boundary may reference multiple defining documents; one ICD may appear on multiple boundary rows.
• No boundary is left blank: each row records either the defining interface documentation or an explicit no-interface determination signed by Systems Engineering (Interface Exists = No-Interface, with SE signoff and date).
• Interface requirement identification is Systems Engineering work; CM maintains this register, verifies coverage (every CI-structure boundary appears here — PROC-001 §5.5.2), and controls the documentation products (§5.5.3).
• Coverage checks run at CI-list submittal for Acquirer concurrence, at each technical review, and prior to each baseline establishment. Record the result and date in the last two columns of each affected row.
• Where MBSE is used, every interface element in the model resolves to a register row and vice versa; record the model element ID.
• Safety-related interfaces (carrying or bounding a hazard risk control) get Safety-Related = Y and the hazard control reference.
Column notes
• Boundary Type: Internal (CI-to-CI within the system), External (system to external system/facility/support equipment), or Control-Level (Acquirer-controlled to Supplier-controlled boundary).
• Controlling Baseline: which baseline the interface requirements belong to via the specification that invokes them (FBL for system-boundary interfaces via the system spec; ABL for CI-to-CI interfaces via item specs). Changes to baselined interfaces are processed through formal change action (Floor ID F37).
• Control Authority: the CCB controlling the defining documentation, and/or ICWG where the Acquirer operates one (Floor ID F38).

## Interface Register
Interface ID | Boundary Type | Side A (CI ID) | Side B (CI ID / External System) | Interface Exists | No-Interface SE Signoff | No-Interface Date | Defining Document(s) | Rev | Controlling Baseline | Control Authority | ICWG-Controlled (Y/N) | MBSE Interface Element ID | Safety-Related (Y/N) | Hazard Control Ref | Coverage Check Result | Coverage Check Date | Notes
IF-0001 | External | CI-0001 | Ground Support System (ext.) | Yes |  |  | ICD-1000-501 | C | FBL | CCB + ICWG | Y | if.AV-GSS | N |  | Covered | 2026-06-15 | System-boundary data link; ICWG rep per PROC-001 §5.5.3
IF-0002 | Internal | CI-0013 | CI-0014 | Yes |  |  | IRS-2210-101; IDD-2211-001 | B; A | ABL | Program CCB | N | if.FCC-OFP | Y | HL-015-C2 | Covered | 2026-06-15 | FCC/OFP execution interface; hosts hazard control
IF-0003 | Internal | CI-0013 | CI-0021 | Yes |  |  | ICD-2200-210 | A | ABL | Program CCB | N | if.FCC-ACT | Y | HL-014-C1 | Covered | 2026-06-15 | Command/monitor loop to elevator actuator
IF-0004 | Control-Level | CI-0012 | CI-0021 | Yes |  |  | PS-2230 §3.3 (interface section) | A | ABL | Program CCB | N | if.FCS-ACT | N |  | Covered | 2026-06-15 | Acquirer/Supplier control boundary; flowdown per SSOW-114
IF-0005 | Internal | CI-0014 | CI-0021 | No-Interface | J. Ramirez, SE Lead | 2026-05-02 |  |  |  |  | N |  | N |  | Covered | 2026-06-15 | No direct OFP-to-actuator interface; all traffic via FCC (IF-0002/0003)

## Lists
Boundary Type | Interface Exists | Controlling Baseline | Control Authority | YN | Coverage Result
Internal | Yes | FBL | Program CCB | Y | Covered
External | No-Interface | ABL | ICWG | N | Open
Control-Level |  | PBL | CCB + ICWG |  | N/A
Internal CCB