## Read Me
FCA Exercise Artifact — Requirements-to-Test Traceability Matrix
Recovery (parachute) subsystem, prepared for its functional configuration audit. This matrix contains seeded defects placed for training. Your task (per the course capstone): audit the matrix, identify every defect, classify each finding, and write one complete request-for-action. Supporting context: the subsystem specification requires DEMONSTRATION BY TEST for all deployment performance requirements (REC-003 through REC-006); requirement REC-014 is a safety-critical hazard-control requirement (arming inhibit) per the hazard analysis; the deficiency report log is on the second sheet. Do not consult the answer key (course appendix) until your findings list is written.

## Traceability Matrix
Req ID | Requirement (summary) | Spec Para | Verif. Method (spec) | Verif. Method (actual) | Test Plan | Test Procedure / Rev | Test Report / Date | Result | Deficiency Report | Notes
REC-001 | Subsystem mass shall not exceed 2.4 kg | 3.2.1 | Inspection | Inspection | — | — | IR-1400-001 / 2026-01-15 | Pass
REC-002 | Stowed envelope per installation drawing | 3.2.2 | Inspection | Inspection | — | — | IR-1400-002 / 2026-01-15 | Pass
REC-003 | Deployment initiation within 150 ms of command | 3.3.1 | Test | Test | VTP-1400 | TP-1400-003 Rev A | TR-1400-008 / 2026-02-20 | Pass
REC-004 | Full canopy inflation within 2.0 s of initiation | 3.3.2 | Test | Analysis | VTP-1400 | — | AN-1400-011 / 2026-02-25 | Pass |  | Verified by inflation model correlation to vendor data
REC-005 | Maximum altitude loss 45 m from deployment command | 3.3.3 | Test | Test | VTP-1400 | TP-1400-005 Rev A | TR-1400-010 / 2026-02-22 | Pass
REC-006 | Descent rate 5.5 m/s ±10% at max gross weight | 3.3.4 | Test | Test | VTP-1400 | TP-1400-006 Rev A | TR-1400-011 / 2026-02-22 | Pass
REC-007 | Deployment loads within airframe attachment limits | 3.3.5 | Test | Test | VTP-1400 | TP-1400-007 Rev B | TR-1400-012 / 2026-02-10 | Pass |  | Procedure Rev B released 2026-03-01 per release record
REC-008 | Operating temperature −20°C to +50°C | 3.4.1 | Test | Test | VTP-1400 | TP-1400-008 Rev A | TR-1400-013 / 2026-03-05 | Pass
REC-009 | Humidity and salt-fog exposure per environmental spec | 3.4.2 | Test | Test | VTP-1400 | TP-1400-009 Rev A | — | Pass |  | Result recorded from test-stand log; no report issued
REC-010 | Pyrotechnic cartridge shelf life ≥ 5 years | 3.5.1 | Analysis | Analysis | — | — | AN-1400-014 / 2026-01-30 | Pass |  | Vendor aging data
REC-011 | Command interface per interface control document | 3.6.1 | Test | Test | VTP-1400 | TP-1400-011 Rev A | TR-1400-015 / 2026-03-08 | Fail (open) | DR-0042 | See deficiency log
REC-012 | Arm/safe status telemetry reporting | 3.6.2 | Test | Test | VTP-1400 | TP-1400-012 Rev A | TR-1400-016 / 2026-03-08 | Pass
REC-013 | Built-in-test fault reporting within 500 ms | 3.6.3 | Test | Test | VTP-1400 | TP-1400-013 Rev A | TR-1400-017 / 2026-03-09 | Fail (open) |  | Deficiency observed; see log
REC-014 | Arming inhibit: deployment shall be inhibited unless armed by two independent conditions (safety-critical hazard control) | 3.7.1 | Test | — | VTP-1400 | — | — | Not verified |  | Sampled out — not in the agreed requirement sample
REC-015 | Repack interval marking and manual coverage | 3.8.1 | Inspection | Inspection | — | — | IR-1400-003 / 2026-03-01 | Pass

## Deficiency Report Log
DR No. | Req ID | Description | Status | Opened
DR-0042 | REC-013 | BIT fault report latency 720 ms vs 500 ms requirement | Open | 2026-03-09
DR-0043 | REC-011 | Command interface checksum mismatch on retry path | Open | 2026-03-08