## Slide 1
SAFETY MANAGEMENT · CONFIGURATION MANAGEMENT
Inherited Assumptions: What Breaks When They Move Between Programs
Programs reuse ground rules and assumptions from earlier programs when the hardware looks similar. The conditions those assumptions depended on do not come with them, and nothing in our current process notices when they change.
Five decisions requested. The control regimes involved are explained on slide 8, glossary at the back.

## Slide 2
EXECUTIVE SUMMARY
The argument on one page
1. What we do today
A new program reusing hardware from an earlier program also reuses that program's assumptions. The sentence is copied. The conditions that made it true are not.
2. Why that is a safety problem
An assumption is a promise that a risk is acceptable so long as certain things stay true. Without the conditions written down, nobody can tell when it has stopped being true.
3. Why programs do it anyway
Rebuilding assumptions costs senior engineering time in the most schedule-compressed phase. The cost is immediate and visible; the risk is deferred and invisible.
4. Where it shows up as exposure
SM-0001 requires a named person to accept residual risk. Inherited assumptions arrive with nobody named. That is a compliance gap, not just untidy engineering.
The proposal
Everything an assumption depends on is already controlled somewhere: engineering drawings and specifications, maintenance program documents, flight and maintenance procedures, training curricula. Each of those has an identifier and a revision. If an assumption records what it depends on and at which revision, we can detect later that it moved. That detection is the thing that does not exist today.
We are not asking programs to slow down or stop reusing. We are asking that reuse leave a trace that can be checked later.

## Slide 3
WHAT WE ARE TALKING ABOUT
An assumption is a conditional promise, not a fact
In safety work an assumption is what lets an analysis stop somewhere. It says a hazard needs no further treatment because something else is taking care of it.
"This hazard is acceptable without additional design mitigation, PROVIDED that the crew is alerted within one flight, the line is inspected every 400 flight hours, and the unit sits outside the icing-exposed bay."
The claim
Short, quotable, and easy to carry to another program. This is the part everyone reads and repeats.
The conditions
Longer, less memorable, and the first thing lost in a copy across. They are what make the claim true.
The risk credit
A hazard was closed without a design change because of this. That is a real safety decision, and someone accepted it.
This is not a new idea
SM-0001 already treats assumptions this way. Appendix 2 lists them among the contents of a hazard record, and the reason given is so they can be re-examined when they change, to check whether the risk assessment still stands. The standard therefore assumes we know when an assumption has changed. For inherited assumptions, we do not.

## Slide 4
WORKED EXAMPLE
A real shape this takes
A pressure sensor is qualified and in service on Program A. Program B is a derivative and reuses the same unit, same part number, same supplier. The assumption set is carried across on that basis.
Program A · what the assumption relied on
Alerting
Crew is alerted to a blocked line within one flight.
Procedure
Dispatch governed by a specific MEL condition.
Inspection
Line inspected every 400 flight hours.
Installation
Unit sits in a heated bay, outside the icing zone.
So
Undetected blockage needs no design mitigation. Hazard closed.
Program B · what is actually different
Alerting
Different avionics supplier, different detection threshold.
Procedure
Different operator, different MEL, rewritten procedure.
Inspection
Customer maintenance program uses 600 flight hours.
Installation
Bay layout changed. Unit now near the icing zone.
So
The part number is identical. Every condition has moved.
Nobody made a mistake. Four teams made four reasonable changes at four different times. No single person ever saw them together next to the assumption they invalidate.

## Slide 5
WHY PROGRAMS REUSE
This is an incentive problem, not a discipline problem
Reuse of assumptions is a rational response to real schedule and cost pressure, and in most cases it produces the right answer. Any proposal that ignores that will be rejected, and should be.
The pressure is real
Assumption sets are written during proposal and early design, the most compressed phase of any program. Rebuilding one costs weeks of senior engineering time the bid does not have.
The incentives point one way
Rebuilding costs the bid, now, visibly. Not rebuilding costs execution or the fleet, years later, invisibly. Every individual decision to reuse is locally sensible.
Reuse is usually correct
When the part, the installation, the environment, the customer and the maintenance program are genuinely the same, the earlier assumption holds and rebuilding it wastes money.
So the problem is not reuse
The problem is reuse in a form nobody can check. If the conditions are not written down and not tied to anything, then when one changes there is no way to find out.
What we are actually asking for
Writing the conditions down at the moment the assumption is made costs minutes, because the engineer making it already knows them. Reconstructing the same conditions three years later costs weeks, and often cannot be done at all. The expensive version of this work is the one we do today.

## Slide 6
WHAT GOES WRONG
The conclusion travels. The conditions stay behind.
What physically moves between programs is the sentence. The reasoning lives in the head of an engineer, in a review held years ago, and in another program's documents.
What arrives
"Undetected blockage needs no design mitigation." One sentence, reviewed and approved, now part of how the new program understands the product.
What stays behind
The alerting threshold, the MEL condition, the inspection interval, the bay location, and the name of whoever accepted the residual risk.
A part number answers only one of these questions
How and where it is installed
How hard it is worked
Temperature, vibration, icing
How often it is inspected
What the crew is alerted to
What it is connected to
How the operator actually flies it
What maintenance requires
A part number is a claim about one box. An assumption is a claim about that box inside a whole aircraft, a whole operation and a whole organization.

## Slide 7
EXPOSURE
Two consequences leadership should care about
1. Risk accepted by nobody
Behind every assumption that closes a hazard there is a person who accepted the residual risk. When the assumption is inherited, that acceptance does not come with it and no equivalent decision is made here.
SM-0001 requires acceptability criteria to be defined and responsibility for accepting risk to be clearly assigned. An inherited assumption still carrying risk credit at critical design review, with nobody named, does not meet that.
2. Cost that compounds by stage
The objection to this work is that it costs time we do not have. That only holds if you compare it against zero rather than against the cost of finding out later.
The cheapest point in the whole lifecycle to capture an assumption is the one point where we currently capture nothing.
Proposal
Write the conditions down while you still know them
Minutes per assumption
Preliminary design
Check against the emerging design
Hours to days, nothing committed yet
Critical design review
Find out it does not hold
Weeks to months, design change and rework
Certification
Find out during compliance demonstration
Months, re-analysis and possible schedule slip
In service
Find out from field evidence
Fleet action, service bulletin, possible AD
Cost shape is illustrative rather than measured across our programs.

## Slide 8
WHERE THE THINGS ASSUMPTIONS DEPEND ON ACTUALLY LIVE
Three control regimes, not one
The facts an assumption relies on are controlled in three different places, by three different authorities, with three different change processes. A practice hooked into only one of them will miss most of the failures.
Engineering configuration control
Drawings, specifications, interface requirements. Changed through a formal engineering change process with a change board. This is where hardware and interface assumptions anchor, and it is the regime we understand best.
Maintenance program and operational control
Inspection intervals, MEL conditions, flight and maintenance procedures. Owned by the operator and the authority, and revised with no engineering change at all. Most of our broken assumptions anchor here.
Training and competence control
Crew and maintainer qualification, recency and curriculum content. Approved and revised through the training organization, entirely outside engineering. Assumptions about human performance anchor here.
What they have in common is enough
All three produce documents with an identifier, a revision and an approval authority. That is all we need to record what an assumption depends on and to detect later that it moved.
Why the SMS has to own this
What they do not share is a single change process, a single owner or a single approval route. That is why this practice has to sit inside the SMS rather than inside any one of the three. Configuration management supplies revision state for the engineering regime and the document-identity discipline that makes references stable. It is a supplier to this practice, not its owner.

## Slide 9
THE OBVIOUS OBJECTION, ANSWERED
We do not have to wait for the design to mature
Assumptions are written at proposal, when almost nothing is fixed. But the documents they can point at appear in sequence, and each one lets a further set of assumptions be anchored.
System specification
Early design
Operating environment and performance assumptions.
Subsystem and interface requirements
Development
Interface, installation, thermal and duty-cycle assumptions.
Detailed design definition
Detail design to CDR
Item-level assumptions, at specific revisions, checkable against the source program.
Maintenance program and procedures
Often late, sometimes customer-owned
Inspection intervals, MEL conditions, crew and maintainer procedures.
Training curricula and qualification
Late, and revised continuously in service
Assumed competence, recency, workload and detection performance.
Note the bottom two. Some assumptions cannot be fully confirmed until the maintenance program and training are settled, which on many programs is at or after entry into service. Those assumptions stay open by design, and saying so honestly is better than recording a confirmation we did not actually make.

## Slide 10
WHAT WE ARE PROPOSING
The fix, in one page
Write the conditions down when the assumption is made
A short record: what is assumed, why, and specifically what has to be true. Written by the person who knows, when they know it. This is the cheap step that unlocks everything else.
Point each condition at a controlled document
If it depends on a 400-hour inspection interval, cite the document that sets the interval rather than repeating the number. Restating is how assumptions go stale silently.
Give every risk-bearing assumption an owner here
Someone on this program accepts the residual risk. Inherited acceptance does not carry over. This is the item SM-0001 already requires.
Sweep for movement, rather than relying on memory
Periodically compare the revision recorded against each assumption with the current revision of that document. Any difference flags the assumption for re-confirmation. No other function has to change how it works.
Count what is still unattached, and report it
Assumptions attach progressively as baselines arrive. The unattached count becomes a design review criterion.
Do not inherit. Re-adopt.
An assumption cannot cross as-is. It is re-adopted after a documented comparison of the two programs covering the conditions, not the part number. Anything unverifiable goes back into risk management.
Five of these six are record-keeping and routing. Only the last costs real engineering time, and only for the small set of assumptions that actually carry risk credit.

## Slide 11
HOW IT ACTUALLY WORKS
The mechanism, and what triggers it
Restated · goes stale silently
"Assumes the line is inspected every 400 flight hours."
When the maintenance program moves to 600 hours, nothing connects that change to this sentence. It stays in the document, still reading as true, for the life of the program.
Referenced · detectable when it moves
"Assumes the inspection interval defined in [document, item, revision]."
When that document is revised, the revision on record no longer matches the one in force, and the next sweep flags it for someone to confirm or reopen.
Why the reference is what makes it work
Recording the document and the revision is what gives you something to compare against later. A restated value gives you nothing: there is no way to tell, looking at the sentence, whether the number in it is still the number in force. This is the whole difference between an assumption that can be checked and one that cannot.
The trigger: a re-confirmation sweep, owned by safety assurance
At set intervals and before every design review, compare the revision recorded against each assumption with the current revision of that document. Any difference flags it for re-confirmation. This works identically for a drawing, a maintenance program document and a training curriculum, because all three carry revisions, and it requires no change to anyone else's process.
Honest trade-off: this finds movement at the next sweep rather than on the day of the change. It is slower than a trigger built into the change process. In exchange it costs no other function anything and it covers all three regimes instead of one.

## Slide 12
KEEPING IT AFFORDABLE
Not every assumption gets the same treatment
If this applies to every assumption on a program it will be rejected, and rightly. The scope decision is made once, early, and it determines whether the practice survives contact with a schedule.
TIER 1
Controlled
Assumptions a hazard analysis or certification finding depends on. Full record, cited documents, named risk acceptor, reported at design reviews.
IN PRACTICE
A small minority. On most programs, tens of items rather than hundreds.
TIER 2
Registered
Assumptions that shape design decisions but carry no safety risk credit. Identifier, owner, statement and reasoning only.
IN PRACTICE
Cheap. Its value is that an item can be promoted to Tier 1 later if analysis shows it is load-bearing.
TIER 3
Engineering note
Everything else: working assumptions, estimating conventions, modeling simplifications with no safety consequence.
IN PRACTICE
No control at all. Saying so explicitly is what keeps Tier 1 credible rather than diluted.
Scope comes out of the hazard analysis, not from a list maintained elsewhere for other purposes. An assumption is Tier 1 if a hazard would reopen when it fails. That judgment is made by the people who already make it, using analysis they already produce, and it is the same judgment SM-0001 already asks for.

## Slide 13
ACTIONS, PART 1 OF 2
What happens when, and who owns it · early lifecycle
Four states, from bid through critical design review. This is where almost all of the value is, because it is where assumptions are created, scoped and last cheaply checkable.
Lifecycle state | What has to happen | Who owns it
Proposal and pre-award | Write down each safety-bearing assumption with its conditions and reasoning as it is made. Record where an inherited one came from and what the similarity claim rested on. Put the cost of discharging them into the bid. | Systems Engineering Program Management
Concept and early design | First hazard analysis decides which assumptions actually carry risk credit; the rest are tiered out. Name a risk acceptor on this program for each one that does. Inherited acceptance does not carry over. | Safety Risk Management SMS
Development and subsystem design | Record what each assumption depends on and at which revision, across all three control regimes. Begin the re-confirmation sweep and report the count still unanchored. | Systems Engineering Human Factors SMS Safety Assurance
Detail design through CDR | Compare source and receiving program condition by condition rather than part number to part number. Anything that cannot be verified goes back into risk management rather than transferring. | Systems Engineering Safety Risk Management
If only two things from this deck are adopted, make them the condition-by-condition comparison at CDR and the re-confirmation sweep on slide 11.

## Slide 14
ACTIONS, PART 2 OF 2
What happens when, and who owns it · later lifecycle
Three states, from verification into service. The work here is mostly about keeping the mechanism running once change volume rises, and about not exporting the same problem to the next program.
Lifecycle state | What has to happen | Who owns it
Verification, audits and certification | Confirm conditions by test, analysis and audit, and move assumptions to verified. An assumption falsified by test is handled as a major change because it affects safety. Confirm assumed task times and alerting by test rather than assertion. | Systems Engineering Quality Human Factors
Production | Keep the sweep running as change volume rises. When a repeated deviation is made permanent, reopen the assumptions it touches. Procedure and training revisions are picked up by the sweep because they carry revisions too. | SMS Safety Assurance Human Factors Configuration Management
In service, and handing on | Field evidence is the only thing that tests assumptions about how the aircraft is actually operated and maintained; route findings to assumption owners. Nothing leaves for the next program without its conditions, references and evidence. | Safety Risk Management SMS Program Management
A program that exports well makes the next program cheaper. A program that exports badly makes it more dangerous.

## Slide 15
BEYOND HARDWARE
Two categories a hardware comparison will never surface
A similarity review compares parts. The assumptions most likely to be wrong are not about parts at all, which is why nothing in the current process catches them.
Assumptions about people
Crew training standard and recency. Workload in the phase of flight concerned. Maintainer skill level. The probability an inspector spots a defect. Time available to complete a procedure. Staffing and fatigue.
These have no part number, so nothing in a parts comparison raises them. Their validity lives in procedures, training and staffing, not in drawings.
The gap: a procedure or training revision generates no engineering change against hardware, so nothing today prompts anyone to ask whether an assumption just broke.
Assumptions about interfaces
Reuse by similarity is a claim about the item. An interface assumption is a claim about the item's surroundings, which is exactly what did not come across.
Technically, the obligation already exists: interface requirements must be identified, documented and change-controlled. Attaching assumptions to them adds a link, not a process.
Organizationally, the classic failure is that the supplier assumed the integrator covered it and the integrator assumed the supplier had. The assumption falls into the gap between two safety management systems.
Why this matters more than the hardware case
In the worked example, three of the four broken conditions are interface or people conditions: the alerting logic, the maintenance program and the crew procedure. The hardware really was identical. That is the pattern, not the exception, and it is why a parts-based similarity argument is not sufficient evidence for carrying an assumption across.

## Slide 16
OWNERSHIP
Who owns what
No single activity owns this end to end today, which is the underlying reason it falls through the cracks. The change from how this was first framed is that the SMS owns the practice and configuration management supports it.
SMS Safety Assurance · owner
Owns the register, the re-confirmation sweep, the named-acceptor rule and the reported position. This practice sits here, not in configuration management.
Safety Risk Management
Decides which assumptions are Tier 1, on the test of whether a hazard reopens if they fail. Reopens those that cannot be verified. Routes in-service findings to assumption owners.
Systems Engineering
Writes the conditions, records the document and revision each one depends on, and performs the source-to-receiving comparison.
Human Factors
Owns assumptions anchored in training and procedure rather than hardware, and validates claims about human performance by test rather than assertion.
Configuration Management · supplier
Supplies revision state for engineering documents and the identifier discipline that keeps references stable. Supporting role. Continued airworthiness and training functions supply the same for the other two regimes.
Program Management
Funds and schedules the work, owns the design review criteria and the reported position, and owns what gets exported to the next program.
Single accountable position: the Safety Accountable Executive, the only role with authority over both the cost pressure and the risk it creates.

## Slide 17
WHAT I AM ASKING FOR
Five decisions
1
Stand the assumption register up under the SMS
Not inside the configuration management plan. The SMS owns the practice end to end; the three control regimes supply revision data to it.
2
Require a named risk acceptor on this program for every Tier 1 assumption
Inherited acceptance does not carry over. This is the item with genuine compliance weight under SM-0001.
3
Run a re-confirmation sweep against recorded revisions
At set intervals and before every design review. No change to the engineering change process and no new field on anyone else's form.
4
Report unanchored and unconfirmed Tier 1 assumptions at design reviews
Program Management owns the position; Safety Assurance owns the measure. Expect the first number to be uncomfortable.
5
Stop releasing bare assumption statements to other programs
The conditions, the document references and the evidence travel with the statement, or nothing travels.
Three honest caveats: no standard requires an assumption register today, so this is a practice we are building rather than an existing obligation. Applied to everything it is unaffordable, so the tiering decision on slide 12 determines whether it survives. And the sweep detects movement at the next sweep, not on the day it happens, which is a real latency we are accepting in order to leave every other process untouched.

## Slide 18
BACK-UP
Glossary and references
Ground rules and assumptions
Statements a program adopts as true to bound analysis and design. In safety work they usually carry risk credit, meaning a hazard was closed partly because of them.
Risk credit
The reduction in assessed risk an assumption provides. If the assumption fails, the credit is withdrawn and the hazard reopens.
Tier 1 assumption
One where a hazard would reopen if the assumption failed. The test is applied by safety risk management using the hazard analysis, not taken from a list held elsewhere.
Anchoring
Recording the specific document, item and revision that each condition of an assumption depends on, rather than restating the value the document contains.
Control regime
One of the three places the underlying facts are controlled: engineering configuration control, maintenance program and operational control, or training and competence control.
Re-confirmation sweep
A periodic comparison of the revision recorded against each assumption with the current revision of that document, flagging any difference for review.
References: SM-0001 Issue C for safety management system and safety risk management requirements. EIA-649-1 and GEIA-HB-649 for configuration management practice, which supports this proposal but does not own it.