CONFIGURATION MANAGEMENT PROCESS

Configuration Audit Process

Functional Configuration Audit (FCA) and Physical Configuration Audit (PCA)

In Alignment with EIA-649-1A and GEIA-HB-649A

Document No.: [XXX-CM-PROC-002]

Revision: [Initial]        Date: [Date]

Prepared by: Configuration Management        Approved by: [Approver]

# Table of Contents

# 1. Purpose, Scope, and Applicability

## 1.1 Purpose

This document instructs the Configuration Management (CM) team on how to plan, conduct, document, and close Functional Configuration Audits (FCAs) and Physical Configuration Audits (PCAs), in alignment with EIA-649-1A §3.5 and GEIA-HB-649A Section 10.

## 1.2 Scope

This process covers common audit responsibilities, audit planning and preparation, FCA conduct, PCA conduct, findings and action item management, post-audit actions, certification, and status accounting of audit results. It applies to hardware CIs, computer software CIs (CSCIs), and firmware, at lower-tier (incremental) and system levels.

## 1.3 Applicability

This process applies to all programs where the company acts as a prime contractor (Supplier) to a DoD Acquirer, including audits conducted at Supplier or sub-supplier facilities. Sub-supplier CIs audited under this process receive equivalent flowed-down requirements. Where a contract imposes differing requirements, the contract governs; deviations are documented in the program Configuration Management Plan (CMP). This process is tool-agnostic.

FCA and PCA may be conducted separately or combined into a single event when there is high confidence that all FCA requirements will be met alongside PCA requirements within the same timeline. A PCA shall not begin unless the corresponding FCA has been successfully completed or is being conducted concurrently.

Sub-supplier audit roles. What a sub-supplier owes when one of its CIs is designated depends on the type of work it performs. Build-to-print suppliers support the PCA on their build (facility access, as-built records, PPSL evidence, and the manufacturing instructions actually used). Suppliers designing and building under a source control drawing, or developing a full item to specification, conduct the item-level FCA and PCA at their facility. Design agents provide technical data package and traceability matrix inputs with no physical examination role. Software and firmware developers conduct the software FCA and the witnessed build and installation verification. Where a supplier holds more than one type of work, the most demanding obligation applies for each obligation rather than by dominant work type. See the sub-supplier CM flow-down process.

Standing conditional audit clause. Award of work to a new or changed sub-tier supplier is itself a designation trigger (Appendix C, C4), so placing a subcontract can create the designation that imposes audit obligations on that same subcontract. Every SOW for a CI where designation is possible shall therefore carry a standing conditional audit clause: conduct or support obligations that take effect if and when the CI is or becomes designated, with the audit deliverables named as triggered items.

# 2. References

## 2.1 Governing Documents

| Document | Title |
| --- | --- |
| EIA-649-1A | Configuration Management Requirements for Defense Contracts (§3.5, Configuration Verification and Audits) |
| GEIA-HB-649A | Configuration Management Standard Implementation Guide (Section 10; Appendices N and P audit checklists) |
| ANSI/EIA-649 | National Consensus Standard for Configuration Management |

## 2.2 Related Documents

| Document | Title / Relevance |
| --- | --- |
| [XXX-CM-PROC-001] | CI Identification Process (companion process; defines the CIs and baselines audited under this process) |
| SM-0001 | Safety Management System (SMS) Standard. Verification of safety-critical requirements identified under the SMS receives priority attention in FCA requirement sampling (see 5.3.3). |
| CM Floor Register | The EIA-649-1A requirements obligated through the SMS pathway on all safety-significant product lines regardless of contract flow-down. Floor items in this process: F29–F31, F34, F42–F44 (see 5.0 note). |
| CM Floor Operating Model | How floor items are dispositioned (perform / documented equivalent control / risk acceptance) via the tailoring gate defined in [XXX-CM-PROC-003] §5.1.1. |
| DI-SESS-81646 | Configuration Audit Plan |
| DI-ADMN-81249 | Conference Agenda |
| DI-ADMN-81250 | Conference Minutes |
| DI-SESS-81022 | Configuration Audit Summary Report |

Data Item Descriptions (DIDs) apply only where cited on contract via CDRL.

# 3. Definitions and Acronyms

## 3.1 Definitions

| Term | Definition |
| --- | --- |
| Functional Configuration Audit (FCA) | The formal audit that verifies the CI’s and system’s tested performance against its approved functional and allocated configuration documentation; confirms specifications and interfaces are accurately and adequately defined; and confirms the Supplier’s change control system adequately controls processing and release of configuration documentation. |
| Physical Configuration Audit (PCA) | The formal examination of the as-built (or as-coded) configuration of a validated CI against its product configuration documentation, verifying the documentation is a clear, complete, and accurate representation of the CI. Successful PCA completion is necessary to establish the product baseline (PBL); all subsequent changes are processed by formal engineering change action. |
| Configuration Verification | The ongoing process, spanning CM, systems engineering, design, test, manufacturing, and quality, by which the design solution is verified: functionally through analyses, inspections, tests, and demonstrations, and physically by inspection and/or process control confirming as-built conformance to as-designed. |
| Action Item / Request for Action (RFA) | The documented record of a discrepancy found during audit proceedings, defining the issue, agreed closure plan, responsible person, and agreed suspense/closure date. RFA is the standard DoD format. |
| Incremental (Capstone) Audit | Audits conducted bottom-up on lower-level CIs, then subsystems, concluding with a final system-level audit confirming all FBL/ABL/PBL requirements are satisfied. Open action items from lower-level audits are carried into system-level minutes. |
| Delta Audit | A follow-on audit of the portion of configuration and verification data that was open (e.g., testing not complete) at the original audit. Delta audit results are added to or supersede the original audit minutes. |

## 3.2 Acronyms

| Acronym | Meaning |
| --- | --- |
| ABL / FBL / PBL | Allocated / Functional / Product Baseline |
| ATP | Acceptance Test Procedure |
| CDR / PDR | Critical / Preliminary Design Review |
| CI / CSCI / HWCI | Configuration Item / Computer Software CI / Hardware CI |
| COTS | Commercial Off-The-Shelf |
| CSA(R) | Configuration Status Accounting (Report) |
| ECP / SCN / NOR / RFV | Engineering Change Proposal / Specification Change Notice / Notice of Revision / Request for Variance |
| FAI | First Article Inspection |
| IDD / VDD / SVD | Interface Design Document / Version Description Document / Software Version Description |
| IMS | Integrated Master Schedule |
| OT&E | Operational Test and Evaluation |
| PPSL | Program Parts Selection List |
| RFA | Request for Action |
| VCRM / RTM | Verification Cross Reference Matrix / Requirements Traceability Matrix |

# 4. Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Configuration Management (CM) | Owns this process. Prepares the audit plan and agenda, coordinates Acquirer approval, assembles and controls the audit data package, records minutes, documents each non-compliance as an RFA and tracks it to closure, prepares the Configuration Audit Summary Report, records results in CSA. |
| Audit Co-Chair (Supplier) | Designated Supplier representative for each audit. Runs proceedings jointly with the Acquirer co-chair, conducts the opening briefing, summarizes side-meeting conclusions into official minutes, conducts management out-briefs. |
| Systems Engineering | Provides the RTM/VCRM, specifications, interface documentation, and analyses. Presents requirement-by-requirement verification evidence at FCA. |
| Design Engineering | Provides released drawings/models, parts lists, product specifications, and change records. Supports as-designed vs. as-built reconciliation at PCA. |
| Test & Evaluation | Provides test plans, procedures, and reports; accounts for tests not yet performed and the plan to accomplish them. |
| Manufacturing / Quality Assurance | Provides manufacturing instructions, process records, QA records, FAI results, and acceptance test data. QA witnesses the software build/installation check at software PCA. Confirms production processes match those used in development or that changes are documented. |
| Sub-suppliers | Participate in planning and conducting audits of their CIs; prepare audit plans identifying their requirements and responsibilities; personnel are prepared to discuss the technical detail of presented material. |
| Acquirer | Approves audit schedule, plan, and agenda. Co-chairs proceedings. Jointly selects the PCA unit. Dispositions audit results as approval, contingent approval, or disapproval. Establishes the PBL after successful PCA. |

# 5. Process

Audits proceed bottom-up: lower-level CIs first, then subsystems, then the system-level audit that verifies achievement of system-level requirements. When audits are conducted in increments, a final (capstone) system-level audit confirms all FBL, ABL, and PBL requirements are satisfied. All entry and exit criteria shall be completed prior to audit closeout.

Relationship to continuous verification. Configuration verification is continuous and embedded: functional verification through the test program, physical verification through inspection and/or process control on every unit, and as-designed/as-built reconciliation performed at scale on data for all CIs through the CSA system (Floor IDs F25–F28, F32–F33). Audits are discrete validations conducted on designated CIs and representative units; their purpose is to confirm that this machinery works — not to substitute for it — and to establish baselines. It is not the intent of an audit to verify every change individually.

CM floor. The following requirements in this process are CM floor items per the CM Floor Register: conducting the FCA to verify performance against the approved FCD/ACD, documenting each FCA non-compliance to the Acquirer, and the requirements-to-test traceability matrix (F42–F44, barrier B16); and conducting the PCA to verify the PCD is consistent with the validated CI, PPSL confirmation and installed-parts verification, documenting each PCA non-compliance to the Acquirer, and identifying differences between the production unit and the FCA unit(s) (F29–F31, F34, barriers B9/B12). On safety-significant product lines these are performed regardless of contract flow-down; any proposal not to perform one is dispositioned through the CM floor gate ([XXX-CM-PROC-003] §5.1.1) and recorded in the program CM Floor Compliance Matrix — never tailored out silently.

## 5.1 Common Requirements (Both FCA and PCA)

Inputs: Designated CI list (5.2.1); IMS; contract and CDRL requirements; released engineering documentation and contract articles; current variance/change listings (RFVs, SCNs, NORs, ECPs).

Outputs: Acquirer-approved audit schedule; co-chair designation; official minutes with recorded discrepancies processed to closure or agreed residual tasks; change/variance implementation verifications.

- Conduct FCAs and PCAs for designated CIs (designated per 5.2.1), including the prime’s designated sub-tier level, and support/participate in audits of related CIs as identified by the Acquirer.

- Establish the schedule, location, and agenda for each audit in consonance with the IMS and obtain Acquirer approval. Hold planning conferences sufficiently in advance (normally 30–60 days) for both parties to prepare.

- Confirm each audit schedule is compatible with the availability of necessary information and contract articles (released engineering documentation, product specifications, quality records, manuals, drawings, reports, hardware, IDD and SVD for software).

- Designate a Supplier representative (co-chair) for the audit.

- Provide a current listing of all RFVs, SCNs, NORs, and ECPs against the CI, either requested or approved.

- Ensure participating Supplier and sub-supplier personnel are prepared to discuss the technical detail of presented material.

- Record significant questions and answers, action items, conclusions, and recommended courses of action in official minutes; summarize side meetings into the main meeting record. Make daily minutes available for joint review at the start of the next session; make overall audit minutes available to the Acquirer before the audit team departs.

- Record all discrepancies and process each to closure or to an agreed residual task with responsible activity and suspense date.

- Verify implementation of engineering changes and variance corrective actions to confirm consistency between the product and its product configuration information.

## 5.2 Audit Planning and Preparation

Inputs: Contract/SOW/CMP audit designations; Appendix C assessments with SMS hazard log, safety data history, and CSA reconciliation health indicators; IMS; prior audit minutes.

Outputs: Audit Designation Assessment Records (Appendix C); Acquirer-approved audit plan (DI-SESS-81646) and agenda (DI-ADMN-81249); assembled and tracked audit data package (Appendices A and B).

### 5.2.1 Audit Designation

CIs requiring FCA/PCA are designated from two sources:

- Contract designation: CIs identified in the contract, SOW, or CMP as requiring audit, including all Acquirer-controlled CIs whose product baseline the Acquirer will establish (PCA completion establishes the PBL).

- Risk-based designation: for CIs not contractually designated, the program shall assess whether an FCA and/or PCA is warranted. Perform the assessment at initial audit planning and repeat it at each CM-plan revision and on any Appendix C trigger event.

Risk-based designation factors (assessed per CI using the Appendix C checklist):

- Safety criticality: CIs implementing or hosting hazard risk controls in the SM-0001 hazard log, and criterion-(b) CIs per [XXX-CM-PROC-001] §5.3, are presumptively designated; omission requires System Safety concurrence.

- Design maturity: new or novel design versus proven heritage; substantive design change since last audit (an SM-0001 management-of-change trigger).

- Production risk: new or changed manufacturing source, process, facility, tooling, or sub-tier supplier.

- Software criticality and single-point-of-failure items.

- History: quality escapes, nonconformances, FOD findings, subcontractor disclosures, work performed not in accordance with approved data, or inaccurate/incomplete manufacturing data findings against the CI or its production line (SM-0001 safety data sources).

- CSA reconciliation health: as-designed/as-built delta aging, unincorporated-change backlog, or serial/effectivity discrepancies indicating the at-scale reconciliation may not be functioning for the CI — the condition audits exist to detect.

Record the assessment and rationale for every CI evaluated, designated or not (Appendix C; retained per Section 6). Internally-initiated audits may be tailored in ceremony (internal co-chair and certification in lieu of Acquirer participation) but not in substance: the requirements-to-test reconciliation and traceability matrix (F42–F44) and the as-built examination including PPSL verification and documented findings (F29–F31, F34) are performed in full. Findings affecting hazard risk controls route per SM-0001.

Single risk factor. Two or more Part C risk factors designate the CI. Exactly one Part C factor does not designate on its own: record the factor, monitor the CI, and reassess against the recorded factor when any further factor arises. Where two or more factors are present and the CI is not designated, the rationale is documented and signed per Appendix C.

### 5.2.2 Audit Plan and Data Package

CM prepares the audit plan (DI-SESS-81646 where contracted) and agenda (DI-ADMN-81249) covering: scope (contract, SOW, specifications), items to be audited (nomenclature, specification numbers, CI identifiers), location, dates, duration, co-chairs, audit team composition and functions, documentation to be reviewed, chronological schedule, and administrative/security requirements.

CM establishes procedures to identify, accumulate, and track availability of required audit artifacts before audit start, and provides them to the audit team. Data package contents are listed per audit type in Appendices A and B.

Contractor resources include the audit plan and agenda, conference facilities, all variances against the CI with status, minutes of prior audits, and personnel from engineering, manufacturing, and quality assurance.

## 5.3 Functional Configuration Audit (FCA)

Inputs: Acquirer-approved FBL and ABL; final draft CI product specification; requirements traceability matrix with test cross-references; test plans, procedures, and reports; ECP/variance listings; PDR/CDR and lower-level audit minutes; Appendix A data package.

Outputs: FCA minutes including the traceability/test matrix; documented non-compliances provided to the Acquirer; action items with closure plans; delta-FCA plan for open verification; verified performance basis supporting product specification approval.

### 5.3.1 Objective and Prerequisites

The FCA verifies the CI’s and system’s performance against its approved functional configuration documentation (FCD) and allocated configuration documentation (ACD), consistent with up-to-date product configuration documentation (PCD); ensures specifications and interfaces are accurately and adequately defined; and confirms the change control system is adequate. For CSCIs, the FCA ensures every requirement has a related test step and the test passes.

- Prerequisite: prior Acquirer approval of the FBL and ABL for the CI or system involved.

- Test data used shall be from verification of the configuration to be formally accepted or released for production (prototype/preproduction article; first production article if none). Where verification can only be completed after system integration and test, the final FCA uses those results.

- Make the final draft CI product specification available to the Acquirer before the FCA, as contracted.

### 5.3.2 Pre-Audit Submittals

Provide to the Acquirer prior to the audit date:

- List of items to be audited, including documents, and the list of tasks to be accomplished at the FCA.

- A traceability matrix for all requirements, cross-referencing test plans, procedures, test programs (including automated test equipment where applicable), and test reports (results of demonstrations, inspections, and analyses per requirement), identifying each known deficiency by deficiency report number. The matrix becomes part of the FCA minutes. (Floor ID F44)

### 5.3.3 Conduct

Open with a design-team briefing per audited item: overview, test results and findings, requirements not met with proposed remedies, ECPs incorporated/tested/proposed, and the overall test effort including problem areas. Then audit systematically:

- Verify the documentation flow for each requirement (or an agreed sampling): baseline requirement specification → test plan → test procedure → test report (or analysis/inspection/demonstration record). Interface requirements are verified as part of this flow.

- Requirements sampling: where sampling is agreed, requirements verified against SMS (SM-0001) hazard controls and other safety-critical requirements are included in the sample, not sampled out.

- Review the complete list of tests accomplished, tests without recorded detail data, tests not yet performed with the plan to accomplish each, and analyses/simulations for requirements not fully verifiable by test.

- Review all approved ECPs and an account of ECPs incorporated and tested as well as proposed.

- For CSCIs additionally: review database characteristics, storage allocation, timing and sequencing against requirements; all documents describing the software product (product specification, user manual, VDD) for format and completeness; developmental configuration change records; the listing of all developmental and non-developmental software versions in the library; and findings of internal CM and SQA audits.

- Examine PDR/CDR minutes to confirm all findings are incorporated and action items closed.

- Review lower-level audit minutes and open action items.

Partial completion may be acknowledged for CIs whose verification is contingent on integrated system testing; document open requirements as action items and close via delta FCA once outstanding testing passes. Delta audit results are added to or supersede the original minutes.

### 5.3.4 Results

Document each non-compliance and provide it to the Acquirer for action. Deliver FCA minutes including the requirements traceability and test matrix. CIs failing quality requirements are analyzed for cause and corrected before re-verification.

## 5.4 Physical Configuration Audit (PCA)

Inputs: Successful or concurrent FCA with minutes per CI; jointly selected production-representative unit; Appendix B data package including drawings/models, manufacturing instructions, ATPs and data, PPSL, VDD/SVD/IDD.

Outputs: PCA minutes; documented non-compliances provided to the Acquirer; certified FCA/PCA-unit difference determination; reconciled as-designed/as-built deltas; basis for Acquirer establishment of the PBL.

### 5.4.1 Objective and Prerequisites

The PCA examines the as-built configuration of a validated CI against its design documentation plus approved changes, verifying the PCD (CAD models, drawings, source code) accurately reflects the validated product, and establishing the final product baseline. The PCA also verifies that any elements redesigned after FCA completion still meet the performance specification, and confirms acceptance testing requirements in the documentation are adequate for production-unit acceptance.

- Prerequisite: FCA successfully completed or conducted concurrently.

- The audited unit is an early production-representative unit selected jointly by the Acquirer and the Supplier.

- Prerequisite: CSA confirms, for the specific unit to be audited, that all work orders are closed and all non-conformance records are dispositioned and closed. Until they are, the unit's as-built configuration is not final, any reconciliation drawn from it is provisional, and the audit would be testing a comparison whose right-hand side can still move.

- A PCA may be conducted after the CI has been embodied in its next higher assembly, provided the CI is acceptable. Embodiment is not a barrier to the audit; in that case the access required extends to the installed CI and to the zone in which it is embodied.

### 5.4.2 Pre-Audit Submittals and Data

Provide item configuration data prior to and at the audit: CI specifications; a list of approved and outstanding changes against the CI; acceptance test procedures and data; engineering drawing index with revision letters; operation and support manuals; approved nomenclature and nameplates; VDDs and Interface Design Documents for software; FCA minutes per CI; QA program findings/status; the PPSL; identification of all changes made during test and required changes not completed; and manufacturing instructions/CAM data for parts identified by the Acquirer. See Appendix B.

Additionally, provide the data the Appendix D check set consumes: material and process certifications traceable to the heat and lot numbers in the unit; part approval, clearance, and qualification records for the installed part types; life-limited and shelf-life records including assigned limits and life consumed at delivery; zone closeout records where the CI is embodied; release records for spares and repair parts provisioned prior to the PCA; and confirmation that inspection and test of sub-supplier end items was completed at point of manufacture.

### 5.4.3 Conduct — Hardware

Perform the PCA check set at Appendix D for every CI designated for PCA. Appendix D states, for each check, what is compared against what and what constitutes a finding; the reconciliation activities below frame that examination. Sampling is per the approved audit plan, except that features implementing or protecting hazard risk controls, and safety-critical characteristics, are included in every sample and are not sampled out. The PCA samples in order to judge whether inspection and process control functioned; it is not a re-inspection of the article.

- Verify item-to-documentation reconciliation: item → drawings → associated lists → parts list; effectivity and next assembly; accuracy of notes and references; referenced released documents.

- Review a representative sample of drawings/3D model data and associated manufacturing instructions (per the approved audit plan) to confirm manufacturing instructions accurately reflect design details and incorporate authorized changes.

- Confirm compatibility with the PPSL and examine the CI to ensure proper parts are actually installed. (Floor ID F30)

- Verify approved changes are incorporated (via CSA reports and selective product data review; the audit validates the reconciliation process, not every change individually). Reconcile and correct any deltas between as-designed and as-built data.

- Identify differences between the PCA unit and the unit(s) used for FCA; certify or demonstrate these differences do not degrade functional characteristics. (Floor ID F34)

- Review completed shortage lists and undocumented design changes; confirm no unapproved changes exist in the technical documentation and all approved changes are incorporated in the hardware.

- Verify that the acceptance testing requirements in the documentation are adequate to accept production units: read the acceptance procedure against the defect modes actually escaping on this CI and its production line. A known escape mode that the acceptance test cannot detect is a finding against the documentation, not against the unit.

- Where the CI's ICD has been revised since a counterpart CI was audited, verify both sides of the interface against the ICD at a common effectivity.

### 5.4.4 Conduct — Software

- Examine the as-coded software against its design/deliverable documentation: compare source code listings to released configuration documentation; verify the VDD including compiler, compiler version, and settings.

- Produce the software build during the PCA, verify it installs on the target device/computer, and verify it against the SVD, witnessed by QA (or the entity designated by the Acquirer), including confirmation that all software updates listed on problem reports for the build are applied.

- Verify the software actually installed in each programmable device (programmable logic, non-volatile memory, microcontrollers): load version, part number, and checksum read back from the device and compared against the version description produced by the witnessed build — not against a value transcribed into a drawing. Where a device cannot be read back, verify the load record for the specific unit, witnessed by QA, with the checksum verified at the point of loading.

- For COTS software: verify correct documentation supporting the versions actually delivered on the media, and adequacy of identification and marking of all deliverable media per contract or best commercial practice.

### 5.4.5 Results and Product Baseline

Document each non-compliance and provide it to the Acquirer. If any inspections, tests, or audits must be re-accomplished, invite the Acquirer or designated representative to witness. When PCAs are incremental, conduct a final system-level PCA to confirm the system PBL is correct. Upon successful PCA completion and product specification approval, the Acquirer establishes the PBL; all subsequent changes are processed by formal engineering change action.

### 5.4.6 System-Level (Capstone) PCA Scope

Where PCAs are conducted in increments, a final system-level PCA confirms the system PBL is correct. The system is itself a CI — normally the top one — and the system-level PCA is scoped to two populations. Neither population is the installation drawing set.

- Child CIs not yet audited, swept against the Appendix C criteria. CIs that now designate are audited as CIs, with their own entry criteria, data package, and lead time. A program accumulates Part D triggers over its life, so a CI that did not designate at award may designate by the time the system is complete.

- Interfaces between CIs, verified against their ICDs at a common effectivity, with the as-built of both sides compared to the interface definition. Prioritize interfaces where both sides are designated CIs, where the interface carries a hazard risk control, or where the ICD has been revised since either side was audited. Each CI's own audit verified its side against its own documentation; no CI-level audit establishes that two CIs meet correctly.

- Baseline coherence: open action items and deltas from earlier increments closed, and effectivity consistent across CIs audited months or years apart. Two audits may each be correct in isolation and describe configurations never approved to sit in the same end item.

Population. The installation drawing set is not the audit population; it is the means of locating what to examine. A sample drawn from drawings rather than from CIs and interfaces is mis-scoped regardless of the percentage sampled, and will concentrate in structure and wiring by drawing volume while no designated CI is audited.

Timing. Run the designation sweep at the CM-plan revision preceding the capstone, not at capstone entry: a newly designating CI requires its own entry criteria, data package, and lead time before the system-level PCA can complete. Confirm the sweep at capstone entry. A CI newly designating at that point is itself a finding on how designation was maintained.

## 5.5 Findings and Action Item Management

Inputs: Discrepancies recorded during audit proceedings (5.3, 5.4); side-meeting conclusions.

Outputs: Classified action items/RFAs with issue, closure plan, owner, and suspense; complete minutes content per this section.

Record every discrepancy as an action item (RFA format where contracted) or in the body of the minutes. Each action item defines the issue, agreed closure plan, responsible person, and suspense/closure date. Classify findings:

- Major: production definition documentation or design data incorrect/incomplete; systematic breakdown of process control; clear non-adherence to workmanship standards; hardware/software not included in the build process; non-adherence to specification/ICD/SOW requirements; FAI data missing or incomplete.

- Minor: non-systematic (e.g., typographical) errors in production definition documentation, process control records, or workmanship standards documentation.

Classification follows the mechanism rather than the instance count. A single instance produced by a systematic breakdown of process control is major; repeated non-systematic errors remain minor.

Minutes content includes: identification of the audited item; decisions and proceedings notes; attendees; action items; complete list of documents with revision level at audit; complete list of specification requirements audited; and identification of documentation and physical products examined (name, specification number, product identifiers, serial numbers, drawing/part numbers, CAGE codes).

For the PCA, the following are provided within the minutes: the complete product drawings and associated lists package with associated manufacturing instruction sheets; completed inspection reports for the selected drawings and their associated manufacturing instructions; records of the configuration baselines for comparison against the engineering change control procedures and release system, including interim releases of spares and repair parts provisioned prior to the PCA; confirmation that inspection and test of sub-supplier end items was completed at point of manufacture; and the PPSL supporting the installed-parts examination.

## 5.6 Post-Audit Actions and Certification

Inputs: Audit minutes and open RFAs (5.5); audit checklist package (completed Appendices A, B, and D); corrective action evidence.

Outputs: Delivered minutes (within 60 days; DI-ADMN-81250); RFA closure records; Configuration Audit Summary Report (DI-SESS-81022); joint certifications; Acquirer disposition; CSA entries of audit dates and results.

- Complete post-audit actions as assigned/directed.

- Publish and deliver finalized minutes to the Acquirer no later than 60 days from audit completion or per contract (DI-ADMN-81250 where cited).

- Track all RFAs/action items to closure; deliver corrective action documentation to the Acquirer for review.

- Prepare the Configuration Audit Summary Report reflecting all action items and discrepancy information from the audit checklist package; issue the detailed final report after Acquirer verification of completed action items (DI-SESS-81022 where cited).

- Complete audit certification: joint certification signatures (Supplier audit lead and PM, Acquirer representatives), with audit results recorded as Complete/Successful (no open worksheets) or Conditional (resolutions agreed, tasks not yet complete). The Acquirer dispositions each audit as Approval (all RFAs satisfactorily completed), Contingent Approval (pending action item completion), or Disapproval (seriously inadequate).

- Record scheduled and actual audit dates, accomplishments, and results in the CSA system for each CI audited.

# 6. Records and Outputs

| Record / Output | Content and Retention |
| --- | --- |
| Audit Designation Assessment Records | Completed Appendix C checklists for every CI evaluated, designated or not, with rationale and sign-offs. Re-performed at CM-plan revisions and trigger events. Retained for the program life. |
| Audit Plan and Agenda | Per 5.2; Acquirer-approved. Retained per program records schedule. |
| Audit Data Package Index | Inventory of artifacts assembled per Appendix A/B with document numbers and revisions at time of audit. |
| Audit Minutes | Per 5.5, including the requirements traceability/test matrix (FCA). Delivered within 60 days of completion. |
| RFA / Action Item Records | Each finding with classification, closure plan, responsible party, suspense, and closure evidence. |
| Configuration Audit Summary Report | Consolidated action item and discrepancy information; final report after verified closure. |
| Audit Certification Forms | Joint FCA/PCA certifications and PM baseline certifications (FBL for FCA; PBL for PCA). |
| CSA Records | Scheduled/actual audit dates and results per CI; PBL establishment entries. |
| Completed Audit Checklist Package | Completed Appendix A/B readiness checklists and the completed Appendix D PCA check set for each CI audited, each check recorded as pass, finding, or not applicable, with findings cross-referenced to RFAs. This is the checklist package the Configuration Audit Summary Report is derived from (5.6). Retained per program records schedule. |

# Appendix A — FCA Data and Readiness Checklist

CI/CSCI: ____________________  Spec No./Rev: ____________________  Audit date: ____________  Co-chairs: ____________________

Entry criteria

| ☐ | Item |
| --- | --- |
|  | FBL and ABL approved by the Acquirer for the CI/system involved |
|  | Audit plan and agenda Acquirer-approved; facilities and audit team confirmed |
|  | Final draft CI product specification provided to the Acquirer |
|  | Pre-audit submittals delivered: item/task lists, requirements traceability matrix with test cross-references and deficiency report numbers |
|  | Audit designation assessment (Appendix C) current for the CI and referenced in the audit plan |

Data package

| ☐ | Item |
| --- | --- |
|  | Specifications (requirements, development, performance, interface) |
|  | Requirements Traceability Matrix and Verification Cross Reference Matrix |
|  | Test plans, procedures, reports/results; analyses; demonstration reports |
|  | Complete lists: tests accomplished (with/without recorded data), tests not yet performed with accomplishment plan, analyses/simulations for non-testable requirements |
|  | Variances (RFVs) relative to the FCA unit(s); current listing of all RFVs, SCNs, NORs, ECPs |
|  | Total list of changes incorporated and/or approved; account of ECPs incorporated, tested, and proposed |
|  | Supplier/sub-supplier SOW and purchase order; minutes of previous sub-system audits; applicable QA records; CSA records |
|  | CSCI only: database/storage/timing/sequencing data; software product documents (product spec, user manual, VDD); developmental configuration change records; software library version listing; internal CM/SQA audit findings |
|  | PDR/CDR minutes with action item status |

Exit criteria

| ☐ | Item |
| --- | --- |
|  | Each requirement (or agreed sample, safety-critical requirements included) reconciled: specification → test plan → procedure → report |
|  | All discrepancies documented as action items with closure plans, owners, suspenses |
|  | Minutes complete, including the traceability/test matrix; management out-brief conducted |
|  | Open verification contingent on system-level test documented; delta FCA planned where required |

# Appendix B — PCA Data and Readiness Checklist

CI/CSCI: ____________________  Part No./Rev: ____________________  Serial No.: ____________  Audit date: ____________

Entry criteria

| ☐ | Item |
| --- | --- |
|  | FCA successfully completed (or concurrent); FCA minutes available per CI |
|  | Audit unit jointly selected; the CI and its detail parts available for examination — isolated, or accessible in situ where the CI is embodied — with specific serial numbers identified |
|  | Unencumbered access to inspection, fabrication, production, assembly, and test facilities and, where the CI is embodied, to the zone in which it is installed; tools, inspection equipment, and test software available |
|  | Final draft CI detail (product) specification available |
|  | CSA confirms for the specific unit: all work orders closed; all non-conformance records dispositioned and closed |
|  | Audit designation assessment (Appendix C) current for the CI and referenced in the audit plan |

Data package

| ☐ | Item |
| --- | --- |
|  | Drawings/3D model data, parts lists, associated lists; engineering drawing index with revisions |
|  | Work instructions / installation procedures / manufacturing instruction sheets / CAM data |
|  | Production acceptance test procedures and associated test data |
|  | Product specifications; operation and support manuals |
|  | List of approved and outstanding changes; identification of changes made during test and required changes not completed |
|  | Variances relative to the PCA unit(s); shortage lists; undocumented design changes review |
|  | PPSL; approved nomenclature and nameplates; QA records and program findings; CSA records; prior sub-system audit minutes |
|  | Software only: source code; software description document; VDD with compiler, version, and settings; SVD; Interface Design Document; deliverable media marking |
|  | Material and process certifications traceable to the heat/lot numbers in the unit |
|  | Part approval, clearance, and qualification records for installed part types |
|  | Life-limited and shelf-life records: designations, assigned limits, life consumed at delivery, cure/expiry evidence |
|  | Zone closeout records where the CI is embodied |
|  | Release records for spares and repair parts provisioned prior to the PCA |
|  | Confirmation of sub-supplier end item inspection and test at point of manufacture |

Exit criteria

| ☐ | Item |
| --- | --- |
|  | Hardware reconciliation complete: item → drawings → associated lists → parts list; effectivity/next assembly; notes and references valid |
|  | Representative drawing/manufacturing-instruction sample reviewed per approved audit plan; authorized changes reflected |
|  | Parts installed match the PPSL; no unapproved changes in documentation; approved changes incorporated in product |
|  | Software build produced, installed, and verified against the SVD, witnessed by QA; problem-report updates confirmed applied |
|  | Differences between the PCA unit and FCA unit(s) identified and certified as non-degrading |
|  | All discrepancies documented as action items; minutes complete; out-brief conducted |
|  | Certification package prepared; PBL establishment recorded in CSA upon Acquirer approval |
|  | Appendix D check set completed for the CI; each check recorded as pass, finding, or not applicable |
|  | Acceptance testing requirements confirmed adequate for production-unit acceptance |

# Appendix C — FCA/PCA CI Selection Checklist

Complete one checklist per CI at initial audit planning, at each CM-plan revision, and on any Part D trigger event. Attach to the Audit Designation Assessment Record (Section 6).

Record the evidence or source relied on for every answer. An answer that has not been established from its source is not a NO: mark it open, assign an owner and a date, and do not sign the assessment until it resolves. Typical sources: contract file and CMP (Part A); SM-0001 hazard log, safety analyses, and program risk matrix (Part B); design history, change records, procurement and process change records, quality and safety data for the CI and its production line, CSA reconciliation health indicators, and prior audit records (Part C).

CI: ____________________  CI identifier: ____________________  Program: ____________________  Assessor/date: ____________________

Part A — Mandatory Designation

| Ref | Question | Yes | No | Evidence / source |
| --- | --- | --- | --- | --- |
| A1 | Is the CI identified in the contract, SOW, or CMP as requiring FCA and/or PCA? |  |  |  |
| A2 | Is the CI an Acquirer-controlled CI whose product baseline the Acquirer will establish (PCA required to establish the PBL)? |  |  |  |

Any YES in Part A → DESIGNATE per the contract scope. Continue to Parts B–D only to determine whether risk factors expand the audit scope (e.g., add a delta audit or earlier increment).

Part B — Safety Criticality (SM-0001). Any YES creates presumptive designation; omission requires documented System Safety concurrence.

| Ref | Question | Yes | No | Evidence / source |
| --- | --- | --- | --- | --- |
| B1 | Does the CI implement or host one or more hazard risk controls recorded in the SM-0001 hazard log? |  |  |  |
| B2 | Is the CI a criterion-(b) CI per [XXX-CM-PROC-001] §5.3 (failure might result in serious injury, loss of life, or loss of primary system capability)? |  |  |  |
| B3 | Per the program safety risk matrix, is the severity of the CI’s credible failure consequence in the highest two severity categories (e.g., catastrophic/hazardous; matrix levels 4–5)? Use the pre-anchored severity where the CM Floor Register records one. |  |  |  |
| B4 | Is the CI safety-critical software, or firmware embedded in a safety-critical device? |  |  |  |
| B5 | Is the CI a single-point-of-failure item for a safety-related function? |  |  |  |

Part C — Risk Factors. Two or more YES answers → designate. Exactly one YES → record and monitor; reassess against the recorded factor when any further factor arises. Where two or more YES answers are present and the CI is not designated, document the rationale and obtain CM and Systems Engineering signature below.

| Ref | Question | Yes | No | Evidence / source |
| --- | --- | --- | --- | --- |
| C1 | Is the design new or novel rather than proven heritage (first-of-type, new technology, unproven margins)? |  |  |  |
| C2 | Has the CI undergone substantive design change since its last audit (SM-0001 management-of-change trigger)? |  |  |  |
| C3 | Is there a new or changed manufacturing source, process, facility, or tooling for the CI? |  |  |  |
| C4 | Is there a new or changed sub-tier supplier for the CI or its critical components? |  |  |  |
| C5 | Does the CI or its production line have a history of quality escapes, nonconformances, FOD findings, or subcontractor disclosures (SM-0001 safety data)? |  |  |  |
| C6 | Have findings of work performed not in accordance with approved data, or of inaccurate/incomplete/ambiguous manufacturing data, been recorded against the CI (SM-0001 safety data)? |  |  |  |
| C7 | Do CSA reconciliation health indicators show anomalies for the CI (as-designed/as-built delta aging, unincorporated-change backlog, serial/effectivity discrepancies)? |  |  |  |
| C8 | Has the CI never received an FCA/PCA, or does a prior audit have an open delta or unresolved action items? |  |  |  |

Part D — Reassessment Triggers. Re-run this checklist for the CI upon any of: substantive design, process, facility, tooling, or supplier change (SM-0001 MoC); new quality escape or safety event traceable to the CI; CSA reconciliation anomaly; hazard log revision adding a risk control to the CI; CM-plan revision.

Disposition

DESIGNATE:  FCA ☐    PCA ☐    Both ☐    Delta audit of open scope ☐        DO NOT DESIGNATE ☐

Audit type if internally initiated: internal co-chair/certification ☐ (substance per 5.2.1 — F42–F44 and F29–F31/F34 performed in full)

Rationale: ________________________________________________________________________

CM: ____________________   Systems Engineering: ____________________   System Safety (required if any Part B yes): ____________________

# Appendix D — PCA Check Set

Perform every check below for each CI designated for PCA (5.4.3). Record each as pass, finding, or not applicable; a check that does not apply is recorded as not applicable, never omitted. Findings are raised as RFAs per 5.5. The completed check set is the audit checklist package from which the Configuration Audit Summary Report is derived (5.6), and is retained per Section 6.

Checks marked [100%] are performed in full. Checks marked [Sampled] are performed against a sample defined in the approved audit plan, except that features implementing or protecting hazard risk controls, and safety-critical characteristics, are included in every sample and are not sampled out. The PCA samples in order to judge whether inspection and process control functioned; it is not a re-inspection of the article, and it cannot verify material, certification, or process conformance by inspection — it verifies the evidence chain, and its findings are breaks in that chain.

CI: ____________________   Part No.: ____________________   Serial No.: ____________   Audit date: ____________

| Check | What is compared, and what constitutes a finding |
| --- | --- |
| 1. Physical item to product definition data | [100%] The CI against the governing revision of its PDD for its effectivity. A part number does not itself carry a revision — the PDD defining the part does, and a change requiring a different part produces a different part number. Finding: the article does not conform to the governing revision, or the governing revision cannot be established from the article and its records without inference. |
| 2. Serialization and traceability | [100%] Serial, batch/lot, and heat numbers physically on the item against the part traceability requirements and against the numbers on the As-Built records. Trace numbers are never re-used and never revised. Life-limited items: designation, assigned limit, and life consumed at delivery. Shelf-life materials: cure/expiry evidence. Finding: any of the three sources disagreeing (two of three agreeing is a finding, not a pass); a life-limited part delivered with no consumed-life record. |
| 3. As-designed to as-built child item reconciliation | [Sampled; 100% for safety-related items] Every child item on the As-Designed dataset against the completed/closed As-Built records (work orders and non-conformance record dispositions), including physically invisible or minor hardware — shims, washers, O-rings, potting compounds, adhesives, thread-locker. Finding: a child item on the As-Designed data with no entry in the build record. Absence in the record is itself the finding; it is not resolved by inspecting the article and concluding the part must be present. |
| 4. Engineering change commitment incorporation | [100% of applicable approved changes] All approved Change Commitments applicable to the CI for the applicable milestone and effectivity, and any temporary redlines or Flight Changes, against the physical unit. Finding: an approved change not incorporated; a change incorporated that was not approved; a temporary marking whose status cannot be established. |
| 5. Non-conformance records and variances | [100%] Every non-conformance on the unit against the adjudication its classification requires, including departures that trip variance gates against the appropriate variance authority. Finding: adjudication by an authority below the classification; an unresolved NCR open against the CI; a recurring variance determined permanently acceptable that should have become an engineering change. |
| 6. Interface and workmanship | [Sampled] Physical dimensions, critical interfaces, connector pinouts, harness routing, ground strap bonding, surface finishes, thermal coatings, and torque stripe application against engineering specifications. Finding: a non-conforming feature, or a conforming feature whose inspection record disagrees with the article — the latter is evidence about the inspection system rather than about the part. |
| 7. Nameplate, marking, and tagging | [100%] Part markings, serial number plates, danger/warning labels, and UID barcodes against the marking instructions in the PDD. Finding: inaccuracy, and equally illegibility, impermanence, or correct marking in an incorrect location. |
| 8. Embedded software and firmware load | [100%] Installed build version, part number, and checksum in each programmable device, read back and compared against the version description produced by the witnessed build — not against a value transcribed into a drawing. Devices that cannot be read back: the load record for this unit, witnessed by QA, with the checksum verified at loading. Finding: a checksum matching a drawing but not the version description; a device with neither read-back nor a witnessed load record. |
| 9. Build traveler and quality buy-off | [Sampled] Shop traveler, inspection logs, and test records against the operations the data requires. Finding: a missing or invalid buy-off; a stamp applied without the authority to apply it; acceptance or inspection data produced by equipment out of calibration, which makes the data inadmissible rather than merely suspect. |
| 10. FCA unit to PCA unit differences | [100%] The PCA unit against the unit(s) used for the FCA, with certification that the differences do not degrade functional characteristics. Identification alone is not sufficient; the certification is the deliverable. Finding: any unidentified difference. “Both were built to the same PDD” is not an answer — tooling, process, source, and workmanship differ between preproduction and production builds even where the design data does not. (Floor ID F34) |
| 11. Manufacturing instructions to product definition data | [Sampled] The sampled PDD against the manufacturing instructions, work instructions, and installation procedures actually used to build the CI, confirming they reflect the design detail at the governing revision and incorporate authorized changes. Finding: an instruction reflecting a superseded revision, or omitting design detail. Check 9 asks whether the traveler was followed; this asks whether the traveler was right — a fully stamped traveler built to a superseded revision passes check 9 and fails the audit. |
| 12. Zone foreign object debris (conditional) | [100% of closed areas] Applicable only where the CI is embodied at the time of the PCA. The zone or area in which the CI is installed, against its closeout records, for tools, loose hardware, swarf, consumables, rags, and packaging. Finding: an area closed with no recorded closeout inspection. Where the CI is not embodied, record as not applicable. |
| 13. Part approval, clearance, and qualification records | [Sampled] The part types installed against their approval, clearance, and qualification records and the PPSL. Finding: a part matching the drawing that was never approved for use; a part de-listed after PDD release through obsolescence, source disqualification, or counterfeit alert; an informal substitution made under shortage pressure. (Floor ID F30) |
| 14. Part certification status and plan status | [100%] The certification and qualification status of the CI and its parts, and the status of the certification plan items applicable at this milestone. Finding: an open plan item nobody can identify, or a certification credit resting on a configuration other than the one audited. An open plan item at this milestone is not automatically a finding. |
| 15. Material and process conformance | [Sampled; 100% for safety-related items] Three links: the material specification in the PDD, against the material note on the As-Built record, against the material certification for the heat/lot number identified in check 2. Special processes (heat treat, plating, coating, NDI) carry process certification in place of the material certificate. Where the PDD permits an equivalent, verify the substitution was approved rather than selected at the bench. Finding: a break anywhere in the chain. A two-link check catches a build record that disagrees with the design; only the third link catches a build record that faithfully records what was ordered when what was delivered differed. |
| 16. Next higher assembly traceability | [100%] The CI's traceability records resolving upward to the next higher assembly, so that fleet-wide lot and heat questions remain answerable after an escape. Where the next higher item in the PDD is a conceptual collector with no physical assembly above it, record that fact and its rationale and trace to the highest physical installation the CI resolves into. Finding: an absent link; a link that does not exist and is recorded as such is not a finding. |
| 17. Sub-supplier end item inspection and test | [Sampled] Completion of inspection and test of sub-supplier end items at point of manufacture, traceable to the articles installed in this unit, with FAI results complete where required. Finding: an installed supplier item with no supporting record; FAI results present but incomplete for a newly sourced part. This confirmation is also provided within the PCA minutes (5.5). |
| 18. Spares and repair parts released before the PCA | [100%] Spares or repair parts for the CI provisioned and released prior to the audit, against the configuration this audit establishes, from the baseline and release records. Finding: a pre-audit release built to a configuration the audit supersedes with the difference neither identified nor dispositioned. Those articles are already in a store or in the field. Records of these interim releases are provided within the PCA minutes (5.5). |

Completed by: ____________________   Date: ____________   CM review: ____________________   Date: ____________