## README
Phase 1 TDR Workbook - EIA-649-1A Compliance Review
Scope statement (put this verbatim in the TDR charter)
The program has no recorded tailoring of EIA-649-1A, so the full standard applies. Phase 1 assesses a defined subset and asserts no compliance position on any requirement outside that subset. The residual is live exposure, is listed on the 'Residual Scope' sheet, and carries a named owner and a dated pass schedule.
Phase 1 is sequenced to remediation capacity, not to calendar convenience.
What is in Phase 1
Block A. The 44 CM floor items (F01 to F44), carried from the CM Floor Register with barrier, hazard, pre-anchored severity, and role mapping intact.
Block B. Section 3 general requirements 3.(1) and 3.(3). 3.(2) and 3.(4) are already floor items F40 and F41.
Block C. The whole of 3.1 Planning and Management, 17 sub-requirements. 3.1.1 and 3.1(1)(e) are the root-cause clauses for the health and staffing findings the rest of the review will surface.
Block D. A slice of 3.2 Configuration Identification, 38 sub-requirements, including unit marking and serialization.
Block E. A slice of 3.4 CSA, 11 sub-requirements. 3.4.1(3)(f) is the as-designed to as-built reconciliation record itself.
Block F. A slice of 3.3, 21 sub-requirements covering change classification criteria and ECP impact-assessment content. 3.3.1.3(1) makes the DD 1692 information set normative through the standard, not through the CDRL.
Two independent scores, deliberately not combined
The HEALTH rung asks whether the activity happens: documented, deployed, operating, effective. It is graded from evidence.
The STAFFING rung asks whether anyone is assigned to make it happen: unassigned, single point, staffed with a credential gap, staffed and credentialed. It is computed from Executor Count and Credential Minimum Met, not entered, so it cannot be graded generously.
They are kept apart because they fail independently. A requirement can be Operating on the strength of one person's diligence and still be one resignation away from Not demonstrated. A requirement can be fully staffed and still not running. Combining them into a single number hides both cases.
The register already carries the DESIGNED allocation in columns L to O, sourced from the enterprise role mapping. Columns W to Z capture the ACTUAL allocation. The delta is the finding, and the Dashboard concentration table is where it becomes visible.
This TDR is internal
Internal changes four things. Evidence does not need to be acquirer-presentable, so query exports, screenshots, and informal record pulls are acceptable and the review moves faster. Independent Reviewer means a different CM function or internal audit, not a customer representative. The tailoring door produces a recommendation to Programs and Contracts, not a closure, because an internal review cannot negotiate relief. And there is no external forcing function, so the dated pass schedule and the named residual owner carry more weight, not less.
One practical consequence worth raising with Contracts and counsel before the first readout: this review will create a dated internal record of known gaps against a standard the contract invokes untailored. That is normal and defensible when each finding carries an owner and a remediation date. It reads differently when it does not. Decide the handling convention up front rather than after the findings exist.
Requirement enumeration for this TDR comes from the body text of the standard, not from the Annex A tailoring worksheet, which does not reconcile to the body. Keep that basis fixed across all passes.
Inclusion rule used to select the non-floor additions
A non-floor clause enters Phase 1 only if it is a root cause of an expected finding, an upstream enabler a floor item depends on, or free because it shares an evidence pull with a floor item already in scope. Column P records which applies.
That rule is expansive. Before the charter goes out, consider tightening it to: an addition qualifies only if a specific floor item is unassessable without it. Applying that test will remove rows.
How to use the register
Columns A to R are sourced. Do not edit them.
Columns S to AQ are the TDR's work. Salmon columns W to Z are the execution-capacity block.
The default when the assessor is deciding between two rungs is the lower one. A claim with no record pull is Not demonstrated. A role with no named individual is Unassigned.
Columns AA, AB, AD, AK, and AN are formulas. Do not overwrite them.
Before assessment begins
Confirm the untailored condition against the SOW invocation and CDRL Block 16, not only against the absence of a completed Annex A worksheet.
Populate the CM Team Roster sheet first. Requirement-level executor names must match roster names exactly for the load counts to work.
Worked example row (format reference, do not copy the values)
Item ID | Clause | Process Ref | Tool | Accountable Owner | Named Executor(s) | Exec Count | Executor Function | Cred Met? | Staffing Rung | Health Rung | Size | Conforming | Disposition
P1-013 | 3.3.1.1(1)(f) | XXX-CM-PROC-003 R.E | PLM release module | J. Okafor (CM Mgr) | A. Rivera | 1 | Change Board Admin | Yes | Single point (computed) | Deployed | 12 | 8 | Gap - remediate
Read the example: the process document exists and the tool is configured, so the item clears Documented and Deployed. The sample shows 8 of 12 conforming, so the health rung stays at Deployed. Separately, one named executor with no backup computes to Single point, and that person sits in Change Board Admin rather than Engineering Release where the register designs the work. Two findings, one row, and neither is visible without the other column.

## Phase 1 Register
Phase 1 Technical Design Review Register - EIA-649-1A
Program: [enter] ¦ Contract / SOW ref: [enter] ¦ TDR Rev / Date: [enter] ¦ Tailoring status: [confirm against SOW and CDRL Block 16 before assessment begins]
Gray columns A-R are sourced. Do not edit. Yellow columns are TDR entries. Salmon columns W-Z are the execution-capacity block. Blue columns are formulas. Columns L to N carry the DESIGNED allocation from the enterprise register; columns W to Z capture the ACTUAL allocation. The delta between them is the finding.
Item ID | Block | TDR Group | EIA-649-1A Clause | Requirement (paraphrased) | Floor ID | Floor Cluster | Barrier(s) | SM-0001 Hazard | Pre-Anchored Severity | Register Inclusion | Designed Owner Tier | Designed Owner Code | Min Credential (designed) | Support Code(s) | Phase 1 Inclusion Basis | Tailorable? | Associated DID / Std | Process / Command Media Ref | Tool / System | Training / Competency Ref | Accountable Owner (name) | Named Executor(s) - who actually performs the work | Executor Count | Primary Executor Function | Credential Minimum Met? | Staffing Rung | Staffing Score | Health Rung | Rung Score | Evidence Type | Evidence Reference | Sample Population | Sample Size | Sample Period | Records Conforming | Conformance % | Disposition | Finding / RFA Ref | Validation Flag | Assessor (name / date) | Independent Reviewer (name / date) | Notes
P1-001 | A. CM Floor (44 items) | 2. Configuration Identification | 3.2.1(2)(b) | Identify as a CI any item whose failure could cause serious injury, loss of life, or loss of primary system capability | F01 | 1. Hazard ID & Critical-Item Recognition | B1 | §6.2.1 Hazard identification | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-82007 | [21 empty] | Not assessed
P1-002 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.2(1) | Classify every engineering change as Major (Class I) or Minor (Class II) | F02 | 1. Hazard ID & Critical-Item Recognition | B2 | §6.2.2 Risk-acceptance authority | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-003 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.2(2)(e)(6)(a) | Treat changes affecting safety as Major (Class I) | F03 | 1. Hazard ID & Critical-Item Recognition | B2 | §6.2.2 Risk-acceptance authority | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-004 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3(3) | Support a joint Acquirer/Supplier Configuration Control Board | F04 | 1. Hazard ID & Critical-Item Recognition | B2 | §6.2.2 Risk-acceptance authority | Catastrophic (1) | Judgment | Tier 3 | 2E | B.S.E. | 2A | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-005 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.8.1(1) | Obtain Acquirer concurrence on Minor (Class II) classification | F05 | 1. Hazard ID & Critical-Item Recognition | B2 | §6.2.2 Risk-acceptance authority | Catastrophic (1) | Judgment | Tier 3 | 2E | B.S.E. | 2A | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-006 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3(1) | Apply configuration control to each CI, its components, and its documentation | F06 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-007 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3(2)(c) | Document, evaluate, disposition, record in CSA, and report changes and variances | F07 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I; 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-008 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3(2)(e) | Incorporate approved changes into all product configuration information and implement them | F08 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-009 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3(2)(f) | Verify approved changes were incorporated | F09 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-010 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1(1) | Use an ECP to document baseline changes and submit to the change approval authority | F10 | 2. Change Discipline & Impact Assessment | B2, B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80639 | [21 empty] | Not assessed
P1-011 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.1(1)(a) | Define the need for each change | F11 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Judgment | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-012 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.1(1)(e) | Incorporate the approved ECP into the configuration documentation | F12 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-013 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.1(1)(f) | Implement and update documentation via a documented engineering release system | F13 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80463 | [21 empty] | Not assessed
P1-014 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.1(1)(g) | Record all changes in the CSA system | F14 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 1 | 2D | A.A.S. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-015 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.1(1)(h) | Verify the approved change was implemented correctly | F15 | 2. Change Discipline & Impact Assessment | B3 | §6.2.1 Work not per approved data | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-016 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.4(1) | Support each ECP with data to evaluate the change and its full impacts | F16 | 2. Change Discipline & Impact Assessment | B4 | §6.2.3 Management of change | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80639 | [21 empty] | Not assessed
P1-017 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.4(3) | Include a summary of testing validating new concepts or technology | F17 | 2. Change Discipline & Impact Assessment | B4 | §6.2.3 Management of change | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80639 | [21 empty] | Not assessed
P1-018 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.2(1) | Obtain Acquirer approval for any non-conforming item via a Request for Variance | F18 | 2. Change Discipline & Impact Assessment | B5 | §6.3.3 Continuous improvement | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I; 2A | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80640 | [21 empty] | Not assessed
P1-019 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.2(2) | Submit an ECP when a variance is determined permanently acceptable (recurring-to-permanent) | F19 | 2. Change Discipline & Impact Assessment | B5 | §6.3.3 Continuous improvement | Catastrophic (1) | Clean (core) | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80640 | [21 empty] | Not assessed
P1-020 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.1.1(1)(c) | Prepare an ECP, NOR, and supporting technical data for the change | F20 | 2. Change Discipline & Impact Assessment | B6 | §6.2.1 Inaccurate/incomplete data | Severe (2) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80639; DI-SESS-80642 | [21 empty] | Not assessed
P1-021 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.4(1) | Submit a NOR for each document affected by an ECP | F21 | 2. Change Discipline & Impact Assessment | B6 | §6.2.1 Inaccurate/incomplete data | Severe (2) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80642 | [21 empty] | Not assessed
P1-022 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.3.4(2) | Provide all information needed to disposition each NOR | F22 | 2. Change Discipline & Impact Assessment | B6 | §6.2.1 Inaccurate/incomplete data | Severe (2) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-80642 | [21 empty] | Not assessed
P1-023 | A. CM Floor (44 items) | 3. Change and Variance Management | 3.2.3.3(1) | Create a new revision of approved documentation after change approval, with before/after traceability | F23 | 2. Change Discipline & Impact Assessment | B7 | §6.2.1 Inaccurate/incomplete data | Severe (2) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-024 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4(1) | Maintain CSA legitimacy by storing valid data | F24 | 3. As-Designed to As-Built Reconciliation | B8 | §6.2.1 Inaccurate manufacturing/maintenance data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-025 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4.1(2) | Capture, store, and maintain product configuration information | F25 | 3. As-Designed to As-Built Reconciliation | B8 | §6.2.1 Inaccurate manufacturing/maintenance data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-026 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4.1(3)(a) | Capture and maintain currently approved configuration information by each CI's identification number | F26 | 3. As-Designed to As-Built Reconciliation | B8, B11 | §6.2.1 / §6.3.2 | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-027 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4.1(3)(c) | Store and manage all product configuration information | F27 | 3. As-Designed to As-Built Reconciliation | B8 | §6.2.1 Inaccurate manufacturing/maintenance data | Catastrophic (1) | Judgment | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-028 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4.1(4)(c) | Secure, safeguard, and retrieve recorded configuration information | F28 | 3. As-Designed to As-Built Reconciliation | B8 | §6.2.1 Inaccurate manufacturing/maintenance data | Catastrophic (1) | Judgment | Tier 2 | 2I | B.S.E.T. | 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-029 | A. CM Floor (44 items) | 4. CSA and Verification | 3.5.3(1) | Conduct the PCA to verify product configuration documentation is consistent with the validated CI | F29 | 3. As-Designed to As-Built Reconciliation | B9 | §6.2.1 Non-conformance / FOD | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81646; DI-SESS-81022 | [21 empty] | Not assessed
P1-030 | A. CM Floor (44 items) | 4. CSA and Verification | 3.5.3(2) | Confirm the CI against the PPSL and verify proper parts are installed | F30 | 3. As-Designed to As-Built Reconciliation | B9 | §6.2.1 Non-conformance / FOD | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-031 | A. CM Floor (44 items) | 4. CSA and Verification | 3.5.3(4) | Document each PCA non-compliance and provide it to the Acquirer | F31 | 3. As-Designed to As-Built Reconciliation | B9 | §6.2.1 Non-conformance / FOD | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I; 2A | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81022 | [21 empty] | Not assessed
P1-032 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4.1(3)(b) | Capture and maintain all historical configuration information with traceability from contract award to present | F32 | 3. As-Designed to As-Built Reconciliation | B10 | §6.3.1 Continued airworthiness data | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-033 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4.1(6) | Document the incorporation of all retrofit changes to units identified for retrofit | F33 | 3. As-Designed to As-Built Reconciliation | B11 | §6.3.2 MoC effectiveness | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81245 | [21 empty] | Not assessed
P1-034 | A. CM Floor (44 items) | 4. CSA and Verification | 3.5.3.1(1)(b) | Identify differences between the production CI and the development CI used for FCA | F34 | 3. As-Designed to As-Built Reconciliation | B12 | §6.2.1 Quality escapes | Severe (2) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-035 | A. CM Floor (44 items) | 2. Configuration Identification | 3.2.5.1(1) | Identify internal and external interface requirements | F35 | 4. Supply Chain, Interfaces & Verification | B13 | §7.3.2 Interface management | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81248 | [21 empty] | Not assessed
P1-036 | A. CM Floor (44 items) | 2. Configuration Identification | 3.2.5.1(2) | Incorporate interface information into the FCD/ACD/PCD | F36 | 4. Supply Chain, Interfaces & Verification | B13 | §7.3.2 Interface management | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81248 | [21 empty] | Not assessed
P1-037 | A. CM Floor (44 items) | 2. Configuration Identification | 3.2.5.1(3) | Maintain configuration control of baselined interface requirements | F37 | 4. Supply Chain, Interfaces & Verification | B13 | §7.3.2 Interface management | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81248 | [21 empty] | Not assessed
P1-038 | A. CM Floor (44 items) | 2. Configuration Identification | 3.2.5.2(1) | Provide a representative to the Acquirer's ICWG where one exists | F38 | 4. Supply Chain, Interfaces & Verification | B13 | §7.3.2 Interface management | Catastrophic (1) | Conditional | Tier 3 | 2E | B.S.E. | 2A | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-039 | A. CM Floor (44 items) | 4. CSA and Verification | 3.4.1(3)(j) | Record and report sub-tier supplier data with traceability to the next higher assembly | F39 | 4. Supply Chain, Interfaces & Verification | B14 | §6.2.1 Subcontractor disclosures | Catastrophic (1) | Clean | Tier 2 | 2I | B.S.E.T. | 2D | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81253 | [21 empty] | Not assessed
P1-040 | A. CM Floor (44 items) | 1. Management and Planning | 3.(2) | Require sub-suppliers to comply with or suitably tailor the same CM requirements imposed on the Supplier | F40 | 4. Supply Chain, Interfaces & Verification | B15 | §6.2.1 + §7 Supply-chain | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2A | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-041 | A. CM Floor (44 items) | 1. Management and Planning | 3.(4) | Support Acquirer audits of Supplier and sub-supplier CM | F41 | 4. Supply Chain, Interfaces & Verification | B15 | §7 Interfaces | Catastrophic (1) | Judgment | Tier 4 | 2A | Advanced / SME | 2E | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-042 | A. CM Floor (44 items) | 4. CSA and Verification | 3.5.2(2) | Conduct the FCA to verify the CI meets performance requirements per approved FCD/ACD | F42 | 4. Supply Chain, Interfaces & Verification | B16 | §6.3.1 Validate risk controls | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81646; DI-SESS-81022 | [21 empty] | Not assessed
P1-043 | A. CM Floor (44 items) | 4. CSA and Verification | 3.5.2(3) | Document each FCA non-compliance and provide it to the Acquirer | F43 | 4. Supply Chain, Interfaces & Verification | B16 | §6.3.1 Validate risk controls | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I; 2A | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | DI-SESS-81022 | [21 empty] | Not assessed
P1-044 | A. CM Floor (44 items) | 4. CSA and Verification | 3.5.2.1(1)(c) | Provide a requirements-to-test traceability matrix (each requirement maps to a test step) | F44 | 4. Supply Chain, Interfaces & Verification | B16 | §6.3.1 Validate risk controls | Catastrophic (1) | Clean | Tier 3 | 2E | B.S.E. | 2I | CM floor. Obligated through the SMS pathway regardless of flow-down. | No | [22 empty] | Not assessed
P1-045 | B. Section 3 general | 1. Management and Planning | 3.(1) | Comply with the CM requirements of this standard as tailored in the contract |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Applicability anchor. The untailored condition is established or refuted here. | Yes | [22 empty] | Not assessed
P1-046 | B. Section 3 general | 1. Management and Planning | 3.(3) | Establish and execute a CM process that controls all configuration documentation representing or comprising the configuration item |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | [22 empty] | Not assessed
P1-047 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(a) | CM planning defines the objectives of the CM program and of each applicable CM element |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-048 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(b) | CM planning defines the appropriate level of CM activity for each CM function across the product life cycle |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-049 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(c) | CM planning defines the CM organization and its organizational relationships |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-050 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(d) | CM planning defines the responsibilities and authority of CM professionals |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-051 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(e) | CM planning defines the CM resources to be used, specifically tools, techniques, training, and methodologies |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause. This clause is the TDR's own analysis axis. | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-052 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(f) | CM planning defines coordination activities with internal and external agencies |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-053 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(g) | CM planning defines the functions, responsibility, and authority of CCBs |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F02 to F05 and F10 | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-054 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(h) | CM planning defines a release process for product configuration documentation |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F13 | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-055 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(i) | CM planning defines methods for determining sub-supplier CM process effectiveness and the actions taken when those processes are ineffective |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F39 to F41 | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-056 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(j) | CM planning defines CSA activities for creating, editing, reviewing, approving, releasing, publishing, and distributing configuration and change documentation |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F24 to F28 | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-057 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1(1)(k) | CM planning defines the identification and labeling structure for configuration items |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F01 and F26 | Yes | DI-SESS-80858; DI-MISC-80508 | [21 empty] | Not assessed
P1-058 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1.1(1) | Include in the CMP a methodology for generating, measuring, and reporting CM performance data |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause. Requires the organization to already know what this TDR will discover. | Yes | [22 empty] | Not assessed
P1-059 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1.1(2) | Make CM performance data available to the Acquirer |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | [22 empty] | Not assessed
P1-060 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1.2(1) | Submit the CM Plan to the Acquirer for review and approval, covering the processes, methods, and procedures used for the assigned CIs over the contract life, and including sub-tier supplier CM performance |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause. The CMP is the controlling document where no tailoring exists. | Yes | DI-SESS-80858 | [21 empty] | Not assessed
P1-061 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1.3(1) | Provide configuration documentation to support each technical review |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of baseline establishment | Yes | [22 empty] | Not assessed
P1-062 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1.4(1) | Address contractually specified product configuration documentation requirements in the CMP, including data handling, processing, storage, retention, integrity, transfer, releasability, security, and maintenance documentation |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F27 and F28 | Yes | [22 empty] | Not assessed
P1-063 | C. 3.1 Planning and Management | 1. Management and Planning | 3.1.4(2) | Inform the Acquirer of any requirements imposed on the Acquirer to maintain the security and integrity of shared data |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Shares an evidence pull with a floor item | Yes | [22 empty] | Not assessed
P1-064 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(1) | Use a documented process for configuration identification |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause of expected health findings | Yes | [22 empty] | Not assessed
P1-065 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(a) | Apply the 3.2.1 criteria to select configuration items |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F01 | Yes | [22 empty] | Not assessed
P1-066 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(b) | Establish a configuration item structure and hierarchy |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F26 and F39 | Yes | [22 empty] | Not assessed
P1-067 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(c) | Select the configuration documentation used to define the configuration baselines for each CI |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F25 and F36 | Yes | [22 empty] | Not assessed
P1-068 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(d) | Identify and control interfaces |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Shares an evidence pull with a floor item | Yes | DI-SESS-81248 | [21 empty] | Not assessed
P1-069 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(e) | Assign enterprise, product, unit, group, and document identifiers to CIs, their component parts, and associated configuration documentation |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F26 | Yes | [22 empty] | Not assessed
P1-070 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(f) | Change the part or identifying number when an item is modified to a non-interchangeable configuration, while retaining the original unit identifier for traceability |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F30 and F33 | Yes | [22 empty] | Not assessed
P1-071 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(g) | Include and affix the design activity CAGE code across CIs, subordinate parts and assemblies, configuration documentation, software media, and products |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of a floor item | Yes | [22 empty] | Not assessed
P1-072 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(h) | Place each item of configuration documentation and software specification under configuration control |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F06 | Yes | [22 empty] | Not assessed
P1-073 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(i) | Establish and manage the functional, allocated, and product baselines at the appropriate points in the CI life cycle |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F10, F36, F42 | Yes | DI-SESS-81121 | [21 empty] | Not assessed
P1-074 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(j) | Mark or label items and documentation with the identifiers that correlate the item, its configuration documentation, and associated data |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F30 | Yes | [22 empty] | Not assessed
P1-075 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2(2)(k) | Obtain Acquirer approval of the type designation and nomenclature for each CI the Acquirer designates for control, tracking, and logistics |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Shares an evidence pull with F05 | Yes | DI-SESS-81254; DI-SESS-81121 | [21 empty] | Not assessed
P1-076 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.1(1) | Select and submit potential configuration items for Acquirer review and selection concurrence |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F01 | Yes | DI-SESS-82007 | [21 empty] | Not assessed
P1-077 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.1(2) | Designate as a CI any item satisfying a system end use function that meets the stated selection criteria. Criterion (b) is floor item F01 and is assessed there. |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F01 | Yes | DI-SESS-82007 | [21 empty] | Not assessed
P1-078 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.1(3)(a) | Assign system product-unique identifiers to software development environment elements in the format specified in the CMP |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F26 where software CIs exist | Yes | DI-SESS-81011 | [21 empty] | Not assessed
P1-079 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.1(3)(b) | Provide a part number representing the device with embedded code where both are controlled through a single altered item drawing |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of a floor item | Yes | DI-SESS-81011 | [21 empty] | Not assessed
P1-080 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.1(3)(c) | Mark the part number and the software medium separately with the supplier code and name identification |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of a floor item | Yes | DI-SESS-81011 | [21 empty] | Not assessed
P1-081 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.1(3)(d) | Designate computer software as configuration items |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F01 | Yes | DI-SESS-81011 | [21 empty] | Not assessed
P1-082 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.2(1) | Use an engineering release process employing formal release records to authorize the use of new or revised configuration documentation |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F13. The floor assumes this system exists but never assesses it. | Yes | DI-SESS-80463 | [21 empty] | Not assessed
P1-083 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.2(2) | Use the engineering release system to issue initial and subsequent approved changes to product configuration documentation, including minor changes |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F08, F12, F13 | Yes | DI-SESS-80463 | [21 empty] | Not assessed
P1-084 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.2(3) | Use the engineering release process to authorize use of configuration documentation associated with an approved configuration |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F13 | Yes | DI-SESS-80463 | [21 empty] | Not assessed
P1-085 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.2(4) | Incorporate approved configuration documentation and the engineering release record into the CSA system |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F14 and F24 | Yes | DI-SESS-80463 | [21 empty] | Not assessed
P1-086 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.3.1(1) | Generate the configuration documentation required for the configuration baselines the Acquirer establishes |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F36 and F42 | Yes | MIL-STD-31000 | [21 empty] | Not assessed
P1-087 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.3.1(2) | Trace each succeeding baseline to its predecessors, including a detailed extension |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F32 and F34 | Yes | [22 empty] | Not assessed
P1-088 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.3.2(1) | Document the functional baseline of the system through functional configuration documentation against the stated content set |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F42 | Yes | [22 empty] | Not assessed
P1-089 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.3.2.1(1) | Document the allocated baseline of a CI through allocated configuration documentation against the stated content set |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F36 and F42 | Yes | [22 empty] | Not assessed
P1-090 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.3.2.2(1) | Document the product baseline of a CI through product configuration documentation against the stated content set |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F29 and F30 | Yes | [22 empty] | Not assessed
P1-091 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.3.2.2(2) | Document the product baseline of a privately developed CI, including the verification provisions required to accept deliveries |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of a floor item | Yes | [22 empty] | Not assessed
P1-092 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4(1) | Uniquely identify each CI, and assign a unique product identifier to each CI and component |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F26 | Yes | [22 empty] | Not assessed
P1-093 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4(2) | Determine the types of configuration documentation required for each CI and component |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F25 | Yes | [22 empty] | Not assessed
P1-094 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4(3) | Assign unique and other identifiers to the CI and to the technical documentation comprising its configuration documentation |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F26 | Yes | [22 empty] | Not assessed
P1-095 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4(4) | Keep the design document identifier the same as, or traceable to, the part or identifying number |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F30 | Yes | [22 empty] | Not assessed
P1-096 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.5.1(4) | Provide interface control documentation for the identified interfaces |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Shares an evidence pull with F35 to F37 | Yes | DI-SESS-81248 | [21 empty] | Not assessed
P1-097 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4.1(1) | Identify all configuration items including their sets, groups, units, assemblies, subassemblies, and parts by marking in accordance with the applicable marking standard |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F30, F32, F33. Unit identification is the precondition for verifying which parts are installed on which unit. | Yes | MIL-STD-130 / MIL-STD-1285 / MIL-STD-13231 | [21 empty] | Not assessed
P1-098 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4.1(2) | Adhere to DoD item unique identification directives, instructions, and standards as tailored in the contract |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F26 and F32 | Yes | MIL-STD-130 | [21 empty] | Not assessed
P1-099 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4.1(3) | Apply IUID marking in accordance with the applicable standard when required by acquisition documents, whether applied direct to the item or by separate means |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F30 and F33 | Yes | MIL-STD-130 / MIL-DTL-15024 | [21 empty] | Not assessed
P1-100 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4.1(4) | Check the DoD IUID registry to confirm a unique item identifier has not been previously assigned before applying it to a configuration item |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F26. A duplicate UII breaks unit-level traceability at the source. | Yes | MIL-STD-130 | [21 empty] | Not assessed
P1-101 | D. 3.2 Configuration Identification slice | 2. Configuration Identification | 3.2.4.2(1) | Mark and label software as specified: embedded identifier and version in source and executable headers, medium labels carrying distribution, ITAR, and classification statements, identifier cross-reference, maturity status, and deliverable media labeling |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Software analogue of unit identification. Applies only where software CIs exist. | Yes | [22 empty] | Not assessed
P1-102 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4(2) | Perform CSA analysis to detect and identify trends and report problems |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause. The floor pulled CSA storage clauses and left the analysis clause behind. | Yes | [22 empty] | Not assessed
P1-103 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(1) | Link the CSA system closely to the data repository used to store and manage product configuration and product operational information |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F24 to F28. The floor assumes this linkage but never assesses it. | Yes | [22 empty] | Not assessed
P1-104 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(3)(d) | Identify dependencies among configuration items |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F16 impact assessment and F39 next-higher-assembly traceability | Yes | DI-SESS-81253 | [21 empty] | Not assessed
P1-105 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(3)(e) | Report the status of both proposed and approved configuration changes and variances against all configuration items |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F07, F14, F18 | Yes | DI-SESS-81253 | [21 empty] | Not assessed
P1-106 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(3)(f) | Record, track, and report implementation status and engineering release of configuration documentation for approved configuration changes |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | The as-designed to as-built reconciliation mechanism. F09 and F15 verify incorporation but depend on this record existing. | Yes | DI-SESS-81253 | [21 empty] | Not assessed
P1-107 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(3)(g) | Record, track, and report the status of corrective actions, including repair and use-as-is, for nonconforming materiel addressed by RFVs where a CI configuration is affected |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F18 and F19 | Yes | DI-SESS-81253 | [21 empty] | Not assessed
P1-108 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(3)(h) | Record and report configuration audit planning and results, including the status and final disposition of identified discrepancies |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Closes the loop on F29, F31, F42, F43. Without it, audit findings have no tracked disposition. | Yes | DI-SESS-81253; DI-SESS-81022 | [21 empty] | Not assessed
P1-109 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(3)(i) | Provide performance metrics that measure the execution of the CM process and its functions |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause. Direct partner of 3.1.1, which is already in scope. | Yes | DI-SESS-81253 | [21 empty] | Not assessed
P1-110 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(4)(a) | Make the CSA system and product configuration information readily available to the Acquirer by on-site inspection, remote access, or scheduled submissions per the contract |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Shares an evidence pull with F41 audit support | Yes | DI-SESS-81253 | [21 empty] | Not assessed
P1-111 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.1(5) | Provide a digital delivery of CSA information and configuration baseline documentation on contract completion, in the form, format, and on the date specified by the CDRL |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Shares an evidence pull with F32 historical traceability | Yes | DI-SESS-81253 | [21 empty] | Not assessed
P1-112 | E. 3.4 CSA reconciliation and reporting | 4. CSA and Verification | 3.4.2(1) | Evaluate CSA corrective actions to verify problems are resolved, adverse trend metrics reversed, changes correctly implemented, and no additional problems introduced |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Root cause and the effectiveness rung's own requirement. | Yes | [22 empty] | Not assessed
P1-113 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.1(1)(b) | Review the product model and other technical data to determine what specific changes will need to be made |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | The technical impact assessment step. F16 requires supporting data; this requires the analysis that produces it. | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-114 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.1(1)(d) | Prepare a separate ECP for each engineering change that has its own distinct objective |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F02. Bundled changes defeat classification. | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-115 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.1(1)(i) | Identify superseding revisions to ECPs, revising an ECP whenever alterations to the initial ECP are necessary |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F12 and F14 | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-116 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.1(1)(j) | Provide an implementation timeline schedule for each ECP |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Schedule impact element of the change assessment | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-117 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.1(1)(k) | State in the ECP any effects on the program if the ECP is not approved |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Consequence-of-not-doing element. Required by CCM-6 and absent from the floor. | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-118 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.1(1)(l) | Notify the Acquirer via ECP of COTS hardware or software changes that may affect interface or interoperability characteristics |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F35 to F37 | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-119 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.3(1) | Use DD Form 1692 or an equivalent form that satisfies the DD 1692-series information requirements for referencing and managing a change |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Makes the DD 1692 content set normative through the standard itself, independent of whether the DID is on the CDRL. This is where the impact-assessment field set enters scope. | Yes | DI-SESS-80639 / DD Form 1692 | [21 empty] | Not assessed
P1-120 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.3(2) | Obtain Acquirer approval before using a supplier-specific ECP format for Major (Class I) or Minor (Class II) ECPs |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Shares an evidence pull with 3.3.1.3(1) | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-121 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.4(2)(a) | Include in the ECP all future production and spare items projected to be procured for the program, where the contract references a life cycle or operation and support cost model |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Cost impact element of the change assessment | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-122 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.4(2)(b) | Include in the ECP all projected operation and support costs for operation of the total inventory by the Acquirer, where the contract references a life cycle or operation and support cost model |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Cost impact element of the change assessment | Yes | DI-SESS-80639 | [21 empty] | Not assessed
P1-123 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.2(2)(a) to (c) | Classify as Major any change to Acquirer-controlled or contract-cited approved documentation, to any physical or functional requirement in approved functional or allocated documentation, or to any Acquirer-owned baseline |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Major-change criteria set. The floor pulled only the safety criterion (F03), leaving the criteria that actually get missed in practice unassessed. | Yes | DD Form 1692 | [21 empty] | Not assessed
P1-124 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.2(2)(d) | Classify as Major any change affecting compatibility with interfacing products, delivered operation or servicing instructions, or required calibration to the extent product identification should change |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Major-change criteria set | Yes | DD Form 1692 | [21 empty] | Not assessed
P1-125 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.2(2)(e)(1) to (5) | Classify as Major any change affecting approved program or project specifications, the software requirements specification, interface characteristics and documents, imposed qualification and acceptance requirements, or other imposed technical requirements documents |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Major-change criteria set | Yes | DD Form 1692 | [21 empty] | Not assessed
P1-126 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.2(2)(e)(6)(b) to (g) | Classify as Major any change affecting approved reliability, maintainability, durability, survivability, or supportability requirements, or producing quantitative attributes outside specified limits or tolerances. Subparagraph (6)(a), safety, is floor item F03. |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Major-change criteria set. F03 covers only the safety criterion from this list. | Yes | DD Form 1692 | [21 empty] | Not assessed
P1-127 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.2(2)(f) to (af) | Apply the remaining Major-change criteria through subparagraph (af), covering operational, support, logistics, training, and non-technical impacts including cost, price, schedule, guarantees, warranties, contracted deliveries, and milestones. Confirm the full enumeration against the standard when assessing. |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Major-change criteria set. Assessed as one row because it is a single evidence pull: sample classified ECPs and test whether the rationale addresses the full criteria set. Annex A enumerates each subparagraph separately. | Yes | DD Form 1692 | [21 empty] | Not assessed
P1-128 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.8(1) | Assign a Minor (Class II) classification only where the change meets no Major criterion, limited to administrative changes, documentation clarifications, corrections, or configuration changes not affecting interchangeability |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Direct partner of F02. The floor requires classification but never assesses the Minor definition. | Yes | DD Form 1692 | [21 empty] | Not assessed
P1-129 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.8.1(2) | Cancel a Minor (Class II) ECP where the Acquirer disagrees with the classification, and revise and resubmit as a Major (Class I) ECP where the change is still required |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Completes the F05 concurrence chain | Yes | [22 empty] | Not assessed
P1-130 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.8.1(3) | Submit unresolved classification disagreements between Supplier and the Acquirer's designated representatives to the Acquirer for final decision |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Completes the F05 concurrence chain | Yes | [22 empty] | Not assessed
P1-131 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.1.8.2(1) | Submit the Minor (Class II) change to the Configuration Approval Authority for concurrence, approval, or disapproval after the classification review and before product delivery |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Upstream enabler of F08. A Minor change delivered without approval is work not per approved data. | Yes | [22 empty] | Not assessed
P1-132 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3.2.2(1) | Use DD Form 1694 content to classify each RFV as Critical, Major, or Minor, applying Critical to departures affecting safety, human health, environment, or security |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | The variance analogue of F03. F18 and F19 are in the floor but variance classification is not, so a safety-affecting departure has no classification gate. | Yes | DI-SESS-80640 / DD Form 1694 | [21 empty] | Not assessed
P1-133 | F. 3.3 Change classification and impact assessment | 3. Change and Variance Management | 3.3(2)(g) | Implement and verify released or approved variance corrective actions |  |  |  |  | Not floor-anchored | N/A |  |  |  |  | Closes the F18 and F19 loop. F09 verifies change incorporation; nothing in the floor verifies variance corrective action. | Yes | [22 empty] | Not assessed

## Lists
Validation lists and scoring
Health Rung | Score | Disposition | Evidence Type | Staffing Rung | Score | Executor Function
Not demonstrated | 0 | Demonstrated | Process document | Unassigned | 0 | Planning and Governance
Documented | 1 | Gap - remediate | Tool configuration | Single point | 1 | Configuration Identification
Deployed | 2 | Gap - recommend tailoring | Training record | Staffed, credential gap | 2 | Change Board Admin
Operating | 3 | Gap - risk accept | Record sample (transactional) | Staffed and credentialed | 3 | Engineering Release
Effective | 4 | Not assessed | Metric or report output |  |  | CSA / Data Management
|  |  | Audit or health check result | Staffing rung is computed, not entered, so it cannot be graded generously. It derives from Executor Count and whether the named executor meets the designed Min Credential in column N. |  | Configuration Audit and Verification
Health score drives the floor gate. Operating (3) is the minimum passing rung. |  | Gap - seek tailoring is available to non-floor items only. | Interview only (insufficient alone) |  |  | Supplier / Sub-tier CM
|  |  | None located |  |  | Shared with Engineering
Shared with Quality
Unassigned

## CM Team Roster
CM Team Roster and Load
Enter every individual who actually performs CM work on this program. Column F counts how many Phase 1 requirements name each person in the register's Named Executor(s) column, so spell names identically in both places. Column G flags concentration.
Concentration thresholds are a starting assumption, not a standard: 25 or more requirements on one individual is High, 15 or more is Watch. Adjust to your organisation and record the basis.
Name | Role title | CM function | Credential held | FTE on this program | Requirements named on | Load flag | Backup named? | Notes
[example] A. Rivera | CM Analyst II | Change Board Admin | B.S.E.T. | 0.8 | 0 |  | No | Example row - delete before use

## Evidence Ladder
Evidence Ladder and Staffing Ladder
Two independent scores. The health rung asks whether the activity happens. The staffing rung asks whether anyone is assigned to make it happen. A requirement can be Operating on heroics with one unbacked individual, and that is a finding even though the records look clean.
Rung | Score | The test | Evidence that satisfies it | Evidence that does not
Not demonstrated | 0 | Nothing located, or the only support is an assertion in interview. | None. | Verbal confirmation. A person's recollection that the activity happens.
Documented | 1 | A controlled process document, procedure, or CMP section states the requirement is performed. | Command media reference with revision and date. | A draft. An unreleased document. A slide deck describing intent.
Deployed | 2 | A tool, workflow, or form exists and is configured to carry the activity, and the responsible role is named. | Tool configuration, workflow definition, form template, named owner in an org record. | A tool that is licensed but not configured. An owner role that is vacant.
Operating | 3 | Records show the activity actually ran across the defined population and period, at the agreed sample size. | Transactional record sample with population, period, size, and conforming count recorded on the register row. | A single example record. A sample drawn only from one program or one month.
Effective | 4 | The records show the control catching real problems, and each finding it raised has a traceable disposition. | Check results including failures, with linked RFA or corrective action records showing closure or active status. | A control that has run for two years and never found anything, with no explanation of why.
Staffing ladder (computed, not entered)
Rung | Score | Condition | What it means | Action
Unassigned | 0 | Executor Count is blank or zero. | No individual performs this requirement. It exists in the process document and nowhere else. | Hard gate. Target is zero. Assign before any other remediation on that row.
Single point | 1 | Executor Count is 1. | One individual carries the requirement with no backup. Records may look clean until that person leaves. | Finding on floor items. Name a backup or fold the work into a shared queue.
Staffed, credential gap | 2 | Executor Count is 2 or more and Credential Minimum Met is not Yes. | Enough people, but at least one does not hold the credential the register designs for the item. | Training or reassignment. Compare against column N.
Staffed and credentialed | 3 | Executor Count is 2 or more and Credential Minimum Met is Yes. | Capacity and competence both present. | None.
How to fill the execution-capacity columns
Accountable Owner and Named Executor(s) are different people and the distinction matters. The owner answers for the requirement; the executor performs it. A requirement with an owner and no executor is unstaffed.
Name individuals, not roles or teams. 'CM' and 'the release team' both resolve to zero named executors. Spell names exactly as they appear on the CM Team Roster sheet.
Primary Executor Function records where the named executor actually sits, not where the register says the work belongs. That mismatch is what surfaces concentration.
Credential Minimum Met compares the executor's held credential against column N of the register, which carries the designed minimum. Unknown is a valid answer and scores the same as No.
A requirement can carry a person who executes it only nominally. If the roster shows one individual named on 40 requirements at 0.5 FTE, the arithmetic is the finding, not the interview.
Sampling rules
Define the population before drawing the sample, and record it on the register row. 'All ECPs' is not a population; 'all ECPs dispositioned on [program] between [date] and [date]' is.
Minimum sample is 10 records per requirement, or the full population where fewer than 10 exist. Record the actual size, not the target.
Sample period is the trailing 12 months unless the requirement is event-driven, in which case use the last 3 occurrences.
Draw across at least two programs where the requirement applies to more than one. A single-program sample cannot support an enterprise conclusion.
The assessor selects the records. A sample supplied by the process owner is evidence of the best case, not of the population.
Disposition doors
Door | When it applies | Availability
Demonstrated | Rung is Operating or Effective, the evidence is on the row, and the requirement has a named executor. | Any item.
Gap - remediate | The requirement applies and is not met. Build, fix, staff, or extend the control. | Any item.
Gap - recommend tailoring | The requirement applies contractually but the activity has no value on this program. This TDR is internal, so the disposition is a recommendation to Programs and Contracts to pursue relief, not a closure. Track it to the recommendation, then reassess. | Non-floor items only.
Gap - risk accept | The gap is known and consciously accepted at the SM-0001 authority for the pre-anchored severity. VP for Severe, CEO for Catastrophic. | Floor items follow SM-0001 authority.
Not assessed | Carried into a later pass. Counts against residual exposure. | Any item.

## Dashboard
Phase 1 TDR Dashboard
Formula driven from 'Phase 1 Register'. Do not overwrite column B.
Scope and completion
Measure | Value
Phase 1 requirements in scope | 133
Floor items (not tailorable) | 44
Non-floor items added | 89
Assessed (disposition entered) | 0
Not yet assessed | 133
Completion % | 0%
Execution capacity gates - target is zero
Measure | Value
Requirements with NO named executor | 133
of which: floor items | 44
Requirements resting on a single individual | 0
of which: floor items | 0
Requirements below the designed credential | 0
Requirements graded Operating or better with no executor | 0
Compliance hard gates - target is zero
Measure | Value
Floor items NOT at Operating or better (includes ungraded) | 44
of which: graded below Operating | 0
of which: not yet graded | 44
Invalid tailoring claims on floor items | 0
Rows flagged by validation | 0
Staffing rung distribution
Measure | Value
Staffed and credentialed | 0
Staffed, credential gap | 0
Single point | 0
Unassigned | 0
Not yet staffing-assessed | 133
Health rung distribution
Measure | Value
Effective | 0
Operating | 0
Deployed | 0
Documented | 0
Not demonstrated | 0
Not yet graded | 133
Disposition distribution
Measure | Value
Demonstrated | 0
Gap - remediate | 0
Gap - recommend tailoring | 0
Gap - risk accept | 0
Floor severity exposure (pre-anchored, not re-rated)
Measure | Value
Catastrophic floor items not at Operating or better | 39
Severe floor items not at Operating or better | 5
Catastrophic floor items with no named executor | 39
Concentration by executor function
This is the load-distribution view. If Change Board Admin and Engineering Release carry most of the register while Identification, Audit, and Supplier CM sit near zero, the organisation has staffed the transactions and not the discipline.
Executor Function | Requirements | Floor requirements | % of register
Planning and Governance | 0 | 0 | 0%
Configuration Identification | 0 | 0 | 0%
Change Board Admin | 0 | 0 | 0%
Engineering Release | 0 | 0 | 0%
CSA / Data Management | 0 | 0 | 0%
Configuration Audit and Verification | 0 | 0 | 0%
Supplier / Sub-tier CM | 0 | 0 | 0%
Shared with Engineering | 0 | 0 | 0%
Shared with Quality | 0 | 0 | 0%
Unassigned | 0 | 0 | 0%
Not yet assigned a function | 133
By TDR group
TDR Group | In scope | Assessed | At Operating or better | Unstaffed | Gaps raised
1. Management and Planning | 21 | 0 | 0 | 21 | 0
2. Configuration Identification | 43 | 0 | 0 | 43 | 0
3. Change and Variance Management | 43 | 0 | 0 | 43 | 0
4. CSA and Verification | 26 | 0 | 0 | 26 | 0
Reading rule
Read the two gate blocks before any distribution. A high completion percentage with a nonzero floor gate is a fail. A requirement graded Operating with no named executor is not operating; it is a record of work someone did once. Execution capacity and compliance evidence are scored separately on purpose, because a process document can pass the second while failing the first. Phase 1 asserts no compliance position on anything outside its scope. See 'Residual Scope'.

## Findings Log
Findings Log
Route every finding into the existing RFA mechanism. Do not maintain a parallel TDR tracker.
Finding ID | Item ID | Clause | TDR Group | Finding type | Finding statement | Health rung | Staffing rung | Root cause (clause ref if upstream) | Severity | RFA Ref | Owner | Target date | Status | Closure evidence | Verified by (name / date)
TDR-0001 | P1-013 | 3.3.1.1(1)(f) | 3. Change and Variance Management | Execution capacity | Release record creation is named to a single CM analyst at 0.8 FTE who is also named on 31 other Phase 1 requirements. No backup named. | Deployed | Single point | 3.1(1)(e) CM resource planning does not allocate release staffing | Catastrophic (1) | RFA-0142 | [name] | 2026-11-30 | Open
Row 5 is an illustrative example. Delete it before use.

## Residual Scope
Residual Scope - what Phase 1 does not cover
The program has no recorded tailoring, so the whole of EIA-649-1A applies. Everything below is live contractual exposure today, not future work. Name an owner for it and report it in every readout.
Clause area | Why deferred | Suggested pass | Owner | Target date
Requirement enumeration basis | Enumeration is taken from the body text of EIA-649-1A, not from the Annex A tailoring worksheet. Annex A does not reconcile cleanly to the body (clause 3.3.1.8.1 appears as 3.3.2.8.1; the software block the body numbers 3.2(3) is placed differently; the DID table cites 3.2.2(5), 3.3.2(5), 3.2.5.1(4), and 3.4.1.5 inconsistently). Keep this basis stated in the charter so later passes count the same way. | Standing decision
3.2.2(5) and 3.3.2(5) | Referenced by the standard's DID table but not extracted during Phase 1 scoping. Probable Phase 1 gaps, not deferrals. | Confirm now, add to Phase 1
3.2.5.2(2)(a) to (d) ICWG membership duties | Conditional on an ICWG existing, same condition as F38. | Pass 2
3.3(2)(a), (b), (d) | Text not extracted during Phase 1 scoping. Confirm against the standard and add to Block F before assessment begins. | Confirm now, add to Phase 1
3.3.1.2(3) and (4); 3.3.2.2(2) and (3) | Text not extracted during Phase 1 scoping. Confirm against the standard. Likely belongs in Block F. | Confirm now, add to Phase 1
3.4.1(4)(b) cyber security for CSA interoperation | Security owner, not CM. Distinct evidence pull. | Parallel workstream, security owner
Lot and batch traceability as an operable control | EIA-649-1A addresses lot and batch only obliquely, through 3.2(2)(e), 3.2(2)(f), and 3.2.4.1 marking. There is no dedicated lot or batch traceability shall. The operable requirement for this organisation more likely sits in AS9100, AS9145, or the contract quality clauses. Assess it against the right source. | Separate scope decision needed
3.2.5 interface management residual beyond F35 to F38 and 3.2.5.1(4) | Remainder of interface clauses not anchored to a barrier. | Pass 2
3.3.1.5 ECP decisions; 3.3.1.6 change priorities; 3.3.1.7.x related engineering changes | Procedural clauses with no floor dependency. | Pass 3
3.3.2.1 recurring variances; 3.3.2.3 RFV decisions; 3.3.2.4 minor RFVs | Variance procedure residual beyond the classification gate in Block F. | Pass 3
3.3.3 Specification Change Notice | Deliverable-bearing, no floor anchor. | Pass 3
3.4 CSA residual beyond Block E | Remaining CSA clauses not pulled into Phase 1. | Pass 3
3.5 verification and audit residual, including 3.5.1, 3.5.4, 3.5.5 | Audit planning, post-audit actions, and audit certification. | Pass 4
DID and CDRL applicability across all cited data items | Contracts analysis, not CM process analysis. Lower priority for an internal review whose purpose is CM capability rather than contract defence. Note that DD 1692 and DD 1694 CONTENT is already in Phase 1 via 3.3.1.3(1) and 3.3.2.2(1), independent of the CDRL. | Parallel workstream, contracts owner
Software CM clauses where software CIs exist | Applicability depends on whether the program has software CIs. Confirm first. | Pass 2 if applicable