[PROGRAM NAME]

Configuration Audit Plan

Functional and Physical Configuration Audits

| Field | Entry |
| --- | --- |
| Program / contract number | [ ] |
| Plan number and revision | [ ] |
| Configuration items covered | [list, or see Section 2] |
| Audit type(s) planned | [Functional / Physical / Combined / Delta] |
| Audit location(s) | [ ] |
| Planned audit date(s) | [ ] |
| Supplier audit co-chair | [name, function] |
| Acquirer audit co-chair | [name, organization] |
| Prepared by | [name, Configuration Management] |
| Date prepared | [ ] |

Approvals

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Configuration Management |  |  |  |
| Program Manager |  |  |  |
| Supplier audit co-chair |  |  |  |
| Quality Assurance |  |  |  |
| Acquirer representative |  |  |  |

Revision history

| Rev | Date | Description of change | Approved by |
| --- | --- | --- | --- |

Guidance:  This is a template. Text in square brackets is filled in for the program. Guidance boxes like this one explain what belongs in each section and are deleted before the plan is issued. Sections that do not apply are marked “not applicable” with a one-line reason — they are not deleted, because a deleted section is indistinguishable from one nobody considered.

# 1.  Purpose and Scope

## 1.1  Purpose

This plan governs the conduct of the functional and physical configuration audits identified in Section 2. It is agreed with the Acquirer before the audits are convened and, once approved, is the controlling document for how those audits are prepared, run, recorded and closed.

## 1.2  Scope

This plan covers: the configuration items to be audited and the basis on which each was designated; the audit approach and sequence; the schedule; the audit team and its responsibilities; the documentation to be reviewed; entry criteria and readiness; how each audit is conducted, including the sampling approach; how findings are classified and closed; and the records the audits produce.

Guidance:  State anything deliberately outside scope here — for example configuration items covered by a separate plan, or audits conducted at a sub-supplier facility under that supplier’s own plan. Name the plan that covers them.

## 1.3  Governing requirements

The audits are conducted in accordance with EIA-649-1A and the following program documents:

| Document | Number / revision | Relevance |
| --- | --- | --- |
| Contract / statement of work | [ ] | Audit requirements, deliverables, and any tailoring |
| Program configuration management plan | [ ] | Program CM requirements and any recorded deviations |
| Applicable configuration item specifications | [ ] | Requirements verified at the functional audit |
| [ ] | [ ] | [ ] |

Where the contract imposes requirements differing from those in this plan, the contract governs and the deviation is recorded here: [record deviations, or state “none”]

# 2.  Configuration Items to be Audited

Guidance:  One row per configuration item. Designation basis is either contractual (named in the contract, statement of work or program CM plan) or risk-based (from the designation assessment). Every item listed must have a current, signed designation assessment on file; reference it in the last column. Items assessed and not designated do not appear here — their assessments are retained separately.

| Configuration item | Item identifier | Specification no. / rev | Audit(s) | Designation basis | Assessment ref. |
| --- | --- | --- | --- | --- | --- |

Audit(s): F = functional, P = physical, C = combined, D = delta audit of open scope.

## 2.1  Designation currency

The designation assessment for each item above is confirmed current at audit entry. An assessment is re-run on any of: substantive design, process, facility, tooling or supplier change; a quality escape or safety event traceable to the item; a reconciliation anomaly; a hazard log revision adding a risk control to the item; or a revision of the program configuration management plan.

Date designation last confirmed for all items in this plan: [  ]

# 3.  Audit Approach

## 3.1  Sequence and prerequisites

Audits proceed bottom-up: lower-level items first, then subsystems, then the system. The following prerequisites apply and are confirmed before each audit convenes.

| Audit | Prerequisite | Confirmed by |
| --- | --- | --- |
| Functional | Acquirer approval of the functional and allocated documentation for the item or system | [ ] |
| Functional | Test data drawn from verification of the configuration being formally accepted or released for production | [ ] |
| Physical | Functional audit successfully completed, or conducted concurrently, with minutes available | [ ] |
| Physical | For the specific unit: all work orders closed and all non-conformance records dispositioned and closed | [ ] |

The physical audit examines the as-built configuration of a validated item, and validation is what the functional audit produces. The order is not a scheduling convention and is not reversed to protect a date.

## 3.2  Combined, incremental and delta audits

Guidance:  State which applies and why. A combined functional and physical event is used only where there is high confidence that the requirements of both can be satisfied in one timeline — it is a decision made from evidence of readiness, not a way to recover schedule. Where verification depends on testing not yet performed, plan the delta audit now rather than treating the gap informally.

Approach for this program: [incremental / combined / delta — with the reasoning]

## 3.3  Audit initiation

Where an audit is initiated internally rather than chaired by the Acquirer, the ceremony may be simplified — an internal co-chair, and internal certification in lieu of Acquirer participation. The substance is performed in full: the requirements-to-test reconciliation and its traceability matrix; the as-built examination including verification that the proper parts are installed; the identification and certification of differences between the production unit and the unit used at the functional audit; and the documentation of every non-compliance.

Initiation for the audits in this plan: [Acquirer-chaired / internally initiated]

# 4.  Schedule

## 4.1  Key dates

| Milestone | Planned date | Owner |
| --- | --- | --- |
| Audit planning conference (30–60 days before the audit) |  |  |
| Plan and agenda submitted to the Acquirer |  |  |
| Plan and agenda approved |  |  |
| Entry criteria complete |  |  |
| Data package complete and provided |  |  |
| Audit convenes |  |  |
| Audit concludes |  |  |
| Minutes delivered (no later than 60 days after completion, or per contract) |  |  |
| Action items closed |  |  |
| Certification and disposition |  |  |

Guidance:  Work backwards from the audit date using each item’s lead time — entry criteria typically 45–60 days out, data package items around 21 days out, and logistics inside the final two weeks. Confirm the audit date is compatible with the actual availability of the information and the contract articles before agreeing it. A date agreed without that confirmation will move.

## 4.2  Chronological schedule of proceedings

| Day / time | Activity | Participants | Location |
| --- | --- | --- | --- |
|  | Opening briefing and administrative brief |  |  |
|  | Design-team briefing per item audited |  |  |
|  | Daily minutes review |  |  |
|  | Management out-brief |  |  |

# 5.  Audit Team and Responsibilities

## 5.1  Co-chairs

The audit is run jointly by a Supplier co-chair and an Acquirer co-chair. The Supplier co-chair gives the opening briefing, folds the conclusions of side meetings into the official record, and delivers the management out-brief.

Supplier co-chair:  ___________________________________________

Acquirer co-chair:  ___________________________________________

## 5.2  Team composition

Guidance:  List names with what each person is there to do — not a distribution list. Most audits that go badly fail on a handoff nobody owned rather than on a judgement.

| Name | Organization / function | Role in the audit | Days required |
| --- | --- | --- | --- |
|  | Configuration Management | Plan and agenda, data package control, minutes, findings, records |  |
|  | Systems Engineering | Traceability matrix, specifications, interface documentation, verification evidence |  |
|  | Design Engineering | Released drawings and models, parts lists, change records, reconciliation support |  |
|  | Test and Evaluation | Test plans, procedures and reports; account of tests not yet performed |  |
|  | Manufacturing | Work instructions, process records, unit and detail part staging, facility access |  |
|  | Quality Assurance | Quality records, first article results, acceptance data, witness of software build |  |
|  | Software | Version descriptions, library listings, build environment and build |  |
|  | System Safety | Concurrence and findings affecting hazard risk controls |  |

## 5.3  Sub-supplier participation

Guidance:  What a sub-supplier owes depends on the type of work it performs, not on its size or relationship. Suppliers who design and build under a source control drawing, or develop a full item to specification, conduct the item-level audits at their own facility. Build-to-print suppliers support the physical audit on their build. Design agents provide data package and traceability inputs. Software and firmware developers conduct the software functional audit and the witnessed build. Where a supplier holds more than one type of work, the most demanding obligation applies for each obligation rather than by dominant type.

| Sub-supplier | Item(s) | Type of work | Audit role | Attending |
| --- | --- | --- | --- | --- |
|  |  |  | Conduct / Support / None |  |

Sub-suppliers whose items are audited participate in planning as well as conduct, prepare audit plans identifying their own requirements and responsibilities, and field personnel able to discuss the technical detail of what is presented.

# 6.  Documentation to be Reviewed

## 6.1  Functional audit data package

| ✓ | Item |
| --- | --- |
|  | Specifications: requirements, development, performance and interface |
|  | Requirements traceability matrix cross-referencing every requirement to test plan, procedure, test program and report — or to the analysis, inspection or demonstration record standing in place of a test — with each known deficiency identified |
|  | Verification cross-reference matrix aligned to the traceability matrix |
|  | Test plans, procedures, and reports or results |
|  | List of tests accomplished; list of tests accomplished without recorded detail data; list of tests not yet performed, each with the plan to accomplish it |
|  | Analyses or simulations standing in place of requirements not fully verifiable by test |
|  | Current listing of every variance, change proposal, specification change notice and revision notice against the item — requested as well as approved |
|  | Account of change proposals incorporated, tested and proposed |
|  | Design review minutes with action item closure status |
|  | Minutes of previous lower-level audits with their open items |
|  | For software: database characteristics, storage allocation, timing and sequencing data; software product documents; developmental configuration change records; library listing of every version held; internal configuration management and software quality audit findings |

## 6.2  Physical audit data package

| ✓ | Item |
| --- | --- |
|  | Drawings and model data, parts lists and associated lists, and the drawing index with revision letters |
|  | Manufacturing instruction sheets, work instructions, installation procedures and machine data for the parts identified |
|  | Approved parts selection list, approved nomenclature and nameplates |
|  | Approval, clearance and qualification records for the part types installed |
|  | Material and process certifications traceable to the heat and lot numbers in the unit |
|  | Life-limited and shelf-life records: designations, assigned limits, life consumed at delivery, cure and expiry evidence |
|  | Production acceptance test procedures and the associated test data for the audit unit |
|  | As-designed to as-built reconciliation report for the audit unit, with change-incorporation reports and the closure status of the unit’s work orders and non-conformance records |
|  | Part traceability records: serial and lot records, safety-critical and special-handling designations, and traceability to the next higher assembly |
|  | Approved and outstanding changes; changes made during test; required changes not completed; shortage lists; review of undocumented design changes; variances applicable to this unit |
|  | Identification of the differences between this unit and the unit(s) used at the functional audit, with the certification that those differences do not degrade functional characteristics |
|  | Quality program findings and status, first article results, and operation and support manuals |
|  | Zone closeout records where the item is embodied |
|  | Release records for spares and repair parts provisioned before the audit |
|  | Confirmation that inspection and test of sub-supplier end items was completed at point of manufacture |
|  | For software: source listings with the released configuration documentation; version description including compiler, version and settings; interface documentation; the build environment staged so a build can be produced during the audit; commercial software documentation matching the delivered media |

# 7.  Entry Criteria and Readiness

## 7.1  Entry criteria

All entry criteria are complete before the audit convenes. A data package item arriving late is a problem to manage. An entry criterion open on the audit date means a precondition of the audit is not satisfied, and the response is a schedule conversation rather than a note in the minutes.

| ✓ | Criterion | Applies to | Owner | Due |
| --- | --- | --- | --- | --- |
|  | Functional and allocated documentation approved by the Acquirer | F |  |  |
|  | Designation assessment current and referenced | F, P |  |  |
|  | Plan and agenda approved; audit team and facilities confirmed | F, P |  |  |
|  | Final draft product specification provided to the Acquirer | F |  |  |
|  | Test data from the configuration being accepted or released | F |  |  |
|  | Functional audit complete or concurrent, with minutes available | P |  |  |
|  | Audit unit jointly selected with the Acquirer; early production-representative; serial numbers identified | P |  |  |
|  | Unit and detail parts available for examination — isolated, or accessible in situ where the item is embodied | P |  |  |
|  | All work orders closed; all non-conformance records dispositioned and closed, for the specific unit | P |  |  |
|  | Unencumbered access to inspection, fabrication, production, assembly and test areas and, where the item is embodied, to its zone; tools, inspection equipment and test software available | P |  |  |
|  | Final draft detail specification available | P |  |  |

## 7.2  Preparation tracking

Preparation is tracked on a working document with one row per required input, each carrying a named provider, a due date derived by working backwards from the audit date, a status, and a location reference so the audit team can find the item rather than ask for it again. Readiness is computed from status rather than declared.

Rows that do not apply to this audit are marked not applicable and retained. A deleted row is indistinguishable from a row nobody thought of.

Location of the preparation tracker: [  ]

Shared with sub-suppliers as the joint punch list: [yes / no — and with whom]

# 8.  Conduct — Functional Audit

Each audited item opens with a design-team briefing covering: an overview of the item; test results and findings; requirements not met, with proposed remedies; change proposals incorporated, tested and proposed; and the overall test effort including its problem areas.

For each requirement, or for the agreed sample, the audit verifies the documentation flow from the baseline requirement to the test plan, to the test procedure, to the test report — or to the analysis, inspection or demonstration record standing in place of a test. Interface requirements are verified within that same flow.

## 8.1  Sampling

| Aspect | Approach for this audit |
| --- | --- |
| Requirements walked in full or sampled | [ ] |
| Sample size and selection method | [ ] |
| Requirements verifying hazard risk controls and other safety-critical requirements | Included in the sample in all cases. Not sampled out. |
| Agreed with the Acquirer on | [date] |

## 8.2  Open verification

Where verification depends on integrated testing not yet performed, partial completion is acknowledged, the open requirements are recorded as action items, and they are closed through a delta audit once the outstanding testing passes. Items failing quality requirements are analysed for cause and corrected before re-verification.

## 8.3  Software items

For software items the audit additionally examines database characteristics, storage allocation, timing and sequencing against the requirements; the software product documents for format and completeness; developmental configuration change records; the library listing of every version held, developmental and non-developmental; and the findings of internal configuration management and software quality audits. The standard applied is that every requirement has a related test step and that test passes.

# 9.  Conduct — Physical Audit

The physical audit verifies that the product documentation is a clear, complete and accurate representation of the unit examined; that anything redesigned after the functional audit still meets the performance specification; and that the acceptance testing requirements in the documentation are adequate to accept production units.

The audit team performs the check set at Appendix B for each item audited. Each check is recorded as pass, finding, or not applicable; a check that does not apply is recorded as not applicable, never omitted.

## 9.1  Sampling

Sample sizes are set in this plan, per check, at Appendix B. Features implementing or protecting hazard risk controls, and safety-critical characteristics, are included in every sample and are not sampled out.

The physical audit samples in order to judge whether inspection and process control functioned. It is not a re-inspection of the article, and it cannot verify material, certification or process conformance by inspection — it verifies an evidence chain, and its findings are breaks in that chain.

## 9.2  Software items

For software items the audit compares source listings against the released configuration documentation; verifies the version description including compiler, compiler version and settings; produces the build during the audit, installs it on the target device and verifies it against the version description, witnessed by Quality Assurance or the entity the Acquirer designates; confirms every update listed on the build’s problem reports is applied; and verifies the load, version, part number and checksum actually installed in each programmable device against that version description.

# 10.  System-Level Audit Scope

Guidance:  Complete this section only where the physical audits under this plan are conducted in increments. Where they are not, state “not applicable — audits are not incremental on this program” and leave the section in place.

Where audits are conducted in increments, a final system-level audit confirms the system product baseline is correct. The system is itself a configuration item — normally the top one — and the system-level audit is scoped to two populations.

| Population | What is audited | Entries for this program |
| --- | --- | --- |
| Child items not yet audited | Swept against the designation criteria. Items that now designate are audited as items, with their own entry criteria, data package and lead time. | [ ] |
| Interfaces between items | Verified against their interface control documents at a common effectivity, with the as-built of both sides compared to the interface definition. Prioritized where both sides are designated items, where the interface carries a hazard risk control, or where the interface document has been revised since either side was audited. | [ ] |

The audit additionally confirms baseline coherence: open action items and deltas from earlier increments closed, and effectivity consistent across items audited months or years apart.

The installation drawing set is not the audit population. It is the means of locating what to examine. A sample drawn from drawings rather than from configuration items and interfaces is mis-scoped regardless of the percentage sampled.

## 10.1  Designation sweep timing

The sweep is run at the program configuration management plan revision preceding the system-level audit, not at its door: an item that newly designates requires its own entry criteria, data package and lead time before the system-level audit can complete. The sweep is confirmed again at entry. An item newly designating at that point is itself a finding on how designation was maintained.

Sweep planned for:  ___________________________________________

Sweep confirmation at entry planned for:  ___________________________________________

# 11.  Findings, Classification and Closure

Every discrepancy found during the audit is recorded with four elements: the issue, stated so that someone who was not present can understand it; the agreed closure plan; the responsible individual, named rather than a department; and the agreed suspense date. There is no verbal finding.

## 11.1  Classification

| Classification | Criteria |
| --- | --- |
| Major | Production definition documentation or design data incorrect or incomplete; systematic breakdown of process control; clear non-adherence to workmanship standards; hardware or software not included in the build process; non-adherence to specification, interface or statement-of-work requirements; first article data missing or incomplete |
| Minor | Non-systematic errors — for example typographical errors in production definition documentation, process control records, or workmanship standards documentation |

Classification follows the mechanism rather than the instance count. A single instance produced by a systematic breakdown is major; repeated non-systematic errors remain minor.

## 11.2  Recording and closure

- A scribe is assigned before the audit begins and finding forms are ready.

- Daily minutes are made available for joint review at the start of the next session; the overall minutes are available to the Acquirer before the audit team departs.

- Side-meeting conclusions are folded into the official record by the co-chair.

- Every non-compliance is documented and provided to the Acquirer for action.

- Action items are tracked to closure and corrective action documentation is delivered to the Acquirer for verification.

Finding record format for this audit: [separate finding records / recorded in the body of the minutes — per contract]

# 12.  Records and Outputs

| Output | Content | Owner | Due |
| --- | --- | --- | --- |
| Findings | Every non-compliance, documented and provided to the Acquirer, and evaluated for the action it requires |  |  |
| Action items | Issue, agreed closure plan, responsible individual, agreed suspense date |  |  |
| Minutes | Audited item; decisions and proceedings; attendees; action items; the complete list of documents with the revision level each carried at the time of the audit; the complete list of specification requirements audited; identification of everything examined by name, specification number, product identifiers, serial numbers, drawing and part numbers, and enterprise code |  |  |
| Minutes — physical audit supporting data | Provided within the minutes: the product drawings and associated lists package with its manufacturing instruction sheets; completed inspection reports for the selected drawings and their associated instructions; records of the configuration baselines for comparison against change control and the release system, including interim releases of spares provisioned before the audit; confirmation of sub-supplier end item inspection and test at point of manufacture; and the parts selection list supporting the installed-parts examination |  |  |
| Rectification records | Evidence that findings and action items have been closed |  |  |
| Summary report | Applicable action items and the discrepancy information derived from the completed check set |  |  |
| Detailed summary report | Prepared only after successful verification that the completed action items are complete, then provided |  |  |
| Witness invitation | Invitation to the Acquirer, or a designated representative, to witness any inspection, test or audit re-accomplished |  |  |
| Completed check set | Appendix B, completed per item audited, with each check recorded and findings cross-referenced |  |  |
| Status accounting entries | Scheduled and actual audit dates, accomplishments and results per item |  |  |

# 13.  Certification and Product Baseline

Audit results are certified jointly by the Supplier audit lead and program manager and the Acquirer’s representatives, and recorded as complete and successful where nothing is open, or conditional where the resolutions are agreed but tasks remain.

The Acquirer dispositions the audit as approval where all findings are satisfactorily completed, contingent approval pending completion of action items, or disapproval where the audit was seriously inadequate.

On successful completion of the physical audit and approval of the product specification, the Acquirer establishes the product baseline for the item. Every subsequent change is processed as formal engineering change action against that baseline.

| Item | Certification | Date | Acquirer disposition | Date |
| --- | --- | --- | --- | --- |
|  | Complete and successful / Conditional |  | Approval / Contingent / Disapproval |  |

# 14.  Administrative and Security Requirements

| Requirement | Detail |
| --- | --- |
| Site access and badging | [ ] |
| Clearance and visit request requirements, with lead times | [ ] |
| Export control and marking requirements | [ ] |
| Facilities: conference space, floor access, staging area for the audit unit | [ ] |
| Network, projection and file transfer arrangements | [ ] |
| Handling of proprietary or classified material during the audit | [ ] |
| Photography and recording restrictions | [ ] |
| Safety briefing and personal protective equipment for floor access | [ ] |

# Appendix A — Audit Preparation Tracker

Guidance:  One row per required input. Derive each due date by working backwards from the audit date. Mark rows that do not apply as not applicable and retain them. Compute readiness from status rather than declaring it.

| Ref | Type | Item required | Provider | Due | Status | Location |
| --- | --- | --- | --- | --- | --- | --- |
|  | Entry criterion |  |  |  |  |  |
|  | Pre-audit submittal |  |  |  |  |  |
|  | Data package |  |  |  |  |  |
|  | Logistics |  |  |  |  |  |

Readiness: ____ of ____ applicable rows complete (____%).  Entry criteria outstanding: ____

# Appendix B — Physical Audit Check Set and Sampling Plan

Guidance:  Complete the sampling column for this program before the plan is approved. Record each check as pass, finding, or not applicable, per item audited. Findings are cross-referenced to their finding record. Features implementing or protecting hazard risk controls, and safety-critical characteristics, are included in every sample and are not sampled out — this is not tailorable.

| Check | What is compared | Sampling | Result |
| --- | --- | --- | --- |
| Physical item to product definition data | The item against the governing revision of its product definition data for its effectivity. A part number does not itself carry a revision; the data defining the part does. | [100% / sample] |  |
| Serialization and traceability | Serial, batch, lot and heat numbers physically on the item against the traceability requirements and against the as-built records. Trace numbers never re-used or revised. Life-limited items: designation, assigned limit, and life consumed at delivery. Shelf-life materials: cure or expiry evidence. | [100% / sample] |  |
| As-designed to as-built child item reconciliation | Every child item on the as-designed dataset against the completed and closed build records, including physically invisible or minor hardware — shims, washers, O-rings, potting compounds, adhesives, thread-locker. Absence in the record is itself the finding. | [100% / sample] |  |
| Engineering change commitment incorporation | All approved change commitments applicable at the milestone and effectivity, and any temporary redlines or flight changes, against the physical unit. | [100% / sample] |  |
| Non-conformance records and variances | Every non-conformance on the unit against the adjudication its classification requires, including departures tripping variance gates. No unresolved record open against the item. | [100% / sample] |  |
| Interface and workmanship | Physical dimensions, critical interfaces, connector pin assignments, harness routing, ground strap bonding, surface finishes, thermal coatings and torque stripe application against the engineering data. | [100% / sample] |  |
| Nameplate, marking and tagging | Part markings, serial number plates, warning labels and unique identification against the marking instructions — accurate, legible, permanently affixed and correctly located. | [100% / sample] |  |
| Embedded software and firmware load | Installed build version, part number and checksum in each programmable device, read back and compared against the version description produced by the witnessed build. | [100% / sample] |  |
| Build traveler and quality buy-off | Traveler, inspection logs and test records against the operations required, with valid stamps or sign-offs and equipment in calibration at the time it produced the data. | [100% / sample] |  |
| Functional audit unit differences | This unit against the unit(s) used at the functional audit, with certification that the differences do not degrade functional characteristics. Identification alone is not sufficient. | [100% / sample] |  |
| Manufacturing instructions to design data | The sampled design data against the manufacturing and work instructions actually used, at the governing revision and incorporating the authorized changes. | [100% / sample] |  |
| Zone foreign object debris (conditional) | Where the item is embodied at the time of the audit: the zone in which it is installed, against its closeout records. Where not embodied, recorded as not applicable. | [100% / sample] |  |
| Part approval, clearance and qualification | The part types installed against their approval, clearance and qualification records and the approved parts selection list. | [100% / sample] |  |
| Certification and plan status | Certification and qualification status of the item and its parts, and the status of the certification plan items applicable at this milestone. | [100% / sample] |  |
| Material and process conformance | Three links: the material specification in the product definition data, against the material note on the as-built record, against the material certification for the heat or lot number. Special processes carry process certification in place of the material certificate. | [100% / sample] |  |
| Next higher assembly traceability | The item’s traceability records resolving upward to the next higher assembly. Where the next higher item is a conceptual collector with no physical assembly above it, that fact and its rationale are recorded. | [100% / sample] |  |
| Sub-supplier end item inspection and test | Completion of inspection and test of sub-supplier end items at point of manufacture, traceable to the articles installed in this unit. | [100% / sample] |  |
| Spares released before the audit | Spares and repair parts provisioned before the audit against the configuration this audit establishes, from the baseline and release records. | [100% / sample] |  |

# Appendix C — Finding Record

Guidance:  One per finding. Copy this page as required, or use the program’s finding record form where the contract specifies one.

| Field | Entry |
| --- | --- |
| Finding number |  |
| Audit and item |  |
| Date raised |  |
| Raised by |  |
| Classification | Major / Minor — with the mechanism that produced the classification |
| Issue | Stated so that someone who was not present can understand it |
| Check or activity that found it |  |
| Agreed closure plan |  |
| Responsible individual | A named person |
| Agreed suspense date |  |
| Closure evidence |  |
| Verified by / date |  |

# Appendix D — Audit Certification

Completed per item audited.

Configuration item:  ___________________________________________

Audit type:  Functional ☐    Physical ☐    Combined ☐    Delta ☐

Audit dates:  ___________________________________________

Location:  ___________________________________________

Certification

Complete and successful ☐    Conditional ☐  — resolutions agreed, tasks remaining as listed in the minutes

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Supplier audit lead |  |  |  |
| Supplier program manager |  |  |  |
| Acquirer representative |  |  |  |
| Acquirer representative |  |  |  |

Acquirer disposition

Approval ☐    Contingent approval ☐ — pending completion of action items    Disapproval ☐

Product baseline established (physical audit):  Yes ☐   Date: ______________   Not yet ☐

Open action items at certification

| Finding no. | Issue | Responsible | Suspense |
| --- | --- | --- | --- |