## Instructions
FCA / PCA Preparation Trackers — Template
Working preparation trackers for Functional and Physical Configuration Audits, implementing [XXX-CM-PROC-002] §5.2–5.4 and Appendices A/B. One workbook per audit event (copy the file; complete the header block). CM owns the tracker; providers own their rows.
How to use
• Complete the header block on each tracker sheet: CI, audit date, and audit type (Acquirer-chaired or internally initiated per PROC-002 §5.2.1). Item Due Dates compute from the Audit Date minus the Lead (days) column — adjust leads to the program's planning conference timeline (normally 30–60 days).
• Each row is one required input: entry criterion, pre-audit submittal, or data package item, drawn from PROC-002 Appendices A/B. Set Status as items arrive; record the Location/Reference (document number, PLM link, room) so the audit team can find it.
• Applicability: N/A rows (e.g., CSCI-only items for a hardware CI, supplier-role scope per the Flowdown Matrix R-17/R-18) are marked Status = N/A, not deleted — the record shows they were considered.
• Supplier-conducted or supplier-supported audits: assign Provider = Supplier for their items per their work-type role ([XXX-CM-GUIDE-002] §3.2) and cite the SDRL (S-10–S-12). The tracker is shareable with the supplier as the joint preparation punch list.
• Readiness % at the top of each sheet computes from Status (Complete + N/A over total). Entry criteria rows must ALL be Complete or N/A before the audit convenes — readiness below 100% on entry criteria at audit start is a schedule conversation, not a footnote.
• Enter dates as date values, not text — the Due Date and overdue logic depend on it.

## FCA Prep Tracker
FCA Preparation Tracker
CI / CSCI: |  | CI ID: |  | Spec No./Rev: |  | Audit Date:
Audit Type: |  | Co-chairs: |  | Prepared by (CM): |  | Readiness: | 0%
Item ID | Category | Required Input | Provider | Lead (days) | Due Date | Status | Location / Reference | Verified By (CM) | Notes
Entry Criteria (all Complete or N/A before audit convenes)
F-01 | Entry criterion | FBL and ABL approved by the Acquirer for the CI/system involved | CM | 60
F-02 | Entry criterion | Audit designation confirmed per PROC-002 §5.2.1 / Appendix C (record ref) | CM | 60
F-03 | Entry criterion | Audit plan and agenda Acquirer-approved (DI-SESS-81646 / DI-ADMN-81249 where cited); facilities and audit team confirmed | CM | 30
F-04 | Entry criterion | Final draft CI product specification provided to the Acquirer | Systems Engineering | 30
F-05 | Entry criterion | Test data is from the configuration to be formally accepted/released for production (prototype/preproduction; first production article if none) | Test & Evaluation | 30
Pre-Audit Submittals
F-06 | Pre-audit submittal | List of items to be audited (including documents) and tasks to be accomplished at the FCA | CM | 30
F-07 | Pre-audit submittal | Requirements traceability matrix: every requirement cross-referenced to test plans, procedures, test programs, and reports (or analysis/inspection/demonstration records), with deficiency report numbers (Floor F44) | Systems Engineering | 30
Data Package — Requirements & Test
F-08 | Data package | Specifications: requirements, development, performance, interface | Systems Engineering | 21
F-09 | Data package | Verification Cross Reference Matrix aligned to the traceability matrix | Systems Engineering | 21
F-10 | Data package | Test plans, procedures, and reports/results; analyses; demonstration reports | Test & Evaluation | 21
F-11 | Data package | Lists: tests accomplished (with/without recorded data); tests not yet performed with accomplishment plan; analyses/simulations for requirements not fully testable | Test & Evaluation | 21
F-12 | Data package | Pre-production test results and qualification status | Test & Evaluation | 21
Data Package — Changes & Variances
F-13 | Data package | Current listing of all RFVs, SCNs, NORs, and ECPs against the CI (requested and approved) | CM | 21
F-14 | Data package | Account of ECPs incorporated and tested, and ECPs proposed | CM | 21
F-15 | Data package | Variances (RFVs) applicable to the FCA unit(s) | CM | 21
Data Package — CSCI-Specific (N/A for hardware-only CIs)
F-16 | Data package | Database characteristics, storage allocation, timing and sequencing data vs. requirements | Software | 21
F-17 | Data package | Software product documents: product specification, user manual, Version Description Document (format and completeness) | Software | 21
F-18 | Data package | Developmental configuration change records; software library listing of all developmental and non-developmental versions | Software | 21
F-19 | Data package | Findings of internal software CM and SQA audits | Quality Assurance | 21
Data Package — Reviews & History
F-20 | Data package | PDR/CDR minutes with action item closure status | Systems Engineering | 21
F-21 | Data package | Minutes of previous lower-level/sub-system audits with open action items | CM | 21
F-22 | Data package | Supplier/sub-supplier SOW and purchase order; applicable QA records; CSA records | CM | 21
Logistics & Facilities
F-23 | Logistics | Conference facilities, projection/network access, security clearances/visit requests | CM | 14
F-24 | Logistics | Design-team opening briefing prepared (overview, results, requirements not met with remedies, ECP account, test effort summary) | Design Engineering | 7
F-25 | Logistics | Daily minutes process and scribe assigned; RFA forms ready | CM | 7

## PCA Prep Tracker
PCA Preparation Tracker
CI / CSCI: |  | CI ID: |  | Spec No./Rev: |  | Audit Date:
Audit Type: |  | Co-chairs: |  | Prepared by (CM): |  | Readiness: | 0%
Item ID | Category | Required Input | Provider | Lead (days) | Due Date | Status | Location / Reference | Verified By (CM) | Notes
Entry Criteria (all Complete or N/A before audit convenes)
P-01 | Entry criterion | FCA successfully completed or being conducted concurrently; FCA minutes available per CI | CM | 60
P-02 | Entry criterion | Audit designation confirmed per PROC-002 §5.2.1 / Appendix C (record ref) | CM | 60
P-03 | Entry criterion | Audit unit jointly selected with the Acquirer: early production-representative unit; serial number(s) identified; item and detail parts isolated | CM | 45
P-04 | Entry criterion | Audit plan and agenda Acquirer-approved; audit team and facilities confirmed | CM | 30
P-05 | Entry criterion | Unencumbered access arranged: inspection, fabrication, production, assembly, and test areas; tools, inspection equipment, and test software available | Manufacturing | 30
P-06 | Entry criterion | Final draft CI detail (product) specification available | Design Engineering | 30
Data Package — Design & Manufacturing
P-07 | Data package | Drawings/3D model data, parts lists, associated lists; engineering drawing index with revision letters | Design Engineering | 21
P-08 | Data package | Manufacturing instruction sheets / work instructions / installation procedures / CAM data for parts identified by the Acquirer | Manufacturing | 21
P-09 | Data package | Drawing/manufacturing-instruction sample selection per the approved audit plan | CM | 21
P-10 | Data package | Program Parts Selection List; nomenclature and nameplate approvals | Design Engineering | 21
Data Package — Acceptance & Records
P-11 | Data package | Production acceptance test procedures and associated test data for the audit unit | Quality Assurance | 21
P-12 | Data package | As-designed/as-built reconciliation report for the audit unit (expressed in PTR identifiers); CSA change-incorporation reports | CM | 21
P-13 | Data package | Part Traceability Records for the audit unit: serials, lot/batch, life-limited designations with limits and life consumed, safety-critical and special handling designations, NHA traceability (Floor F39) | Quality Assurance | 21
P-14 | Data package | List of approved and outstanding changes; changes made during test; required changes not completed; shortage lists; undocumented design change review | CM | 21
P-15 | Data package | Variances applicable to the PCA unit(s) | CM | 21
P-16 | Data package | Identification of differences between the PCA unit and the FCA unit(s), with certification basis that differences do not degrade functional characteristics (Floor F34) | Systems Engineering | 21
P-17 | Data package | QA program findings/status; FAI results | Quality Assurance | 21
P-18 | Data package | Operation and support manuals | Logistics | 21
Data Package — Software-Specific (N/A for hardware-only CIs)
P-19 | Data package | Source code and released configuration documentation for comparison | Software | 21
P-20 | Data package | VDD including compiler, compiler version, and settings; SVD; Interface Design Document | Software | 21
P-21 | Data package | Build environment staged: build produced during PCA, installed on target, verified against SVD, witnessed by QA; problem-report updates confirmed applied | Software | 14
P-22 | Data package | COTS software: documentation matching delivered versions; deliverable media identification and marking | Software | 21
Reviews & History
P-23 | Data package | FCA minutes per CI; minutes of previous sub-system PCAs with open action items | CM | 21
P-24 | Data package | CSA records; sub-supplier SOW/PO where supplier-built (role per Flowdown Matrix R-18) | CM | 21
Logistics & Facilities
P-25 | Logistics | Audit unit staged with detail parts; inspection equipment calibrated and available | Manufacturing | 7
P-26 | Logistics | Conference facilities, security clearances/visit requests; daily minutes process and scribe; RFA forms ready | CM | 7