## Summary
CM Floor Requirements — Process Document Traceability
Traces all 44 CM floor requirements to the generated process documents that fulfill them, and identifies gaps. Status legend: Fulfilled = a generated Level III process performs the requirement; Partial = planned in the CM plan or referenced as continuous machinery, but no generated process performs it; Not fulfilled = no coverage in the generated set.
The generated set: CI Identification Process, Configuration Audit Process (FCA/PCA), and CM Planning & Management Process — three of the five CM functions. Every gap traces to one of the two functions not yet written as their own process: Change Management (EIA-649-1A §3.3) and Status Accounting (EIA-649-1A §3.4).
Tally
Fulfilled | 15
Partial (planned/referenced, not performed) | 9
Not fulfilled | 20
Total | 44
Gap ownership
• Change Management process (§3.3) — unwritten — owns F02, F05–F13, F15–F23 (fully) and F03/F04/F23 (jointly with the CM plan). 19 of the 21 not-fulfilled requirements. This is the highest-value document to write next.
• Status Accounting process (§3.4) — unwritten — owns F14, F24, F26 (fully) and hardens partials F25/F27/F28/F32/F33. Second priority.
• Interim control: the CM plan floor gate lets any program disposition F02–F28 consciously (perform / equivalent / risk-accept), so nothing is silently dropped — but a gate disposition is not a performing process.

## Traceability
Floor ID | Cluster | Clause | Requirement (paraphrased) | Barrier | Status | Fulfilling / Owning Document | Section(s) | Trace rationale / explanation
F01 | 1. Hazard ID & Critical-Item Recognition | 3.2.1(2)(b) | Identify as a CI any item whose failure could cause serious injury, loss of life, or loss of primary system capability | B1 | Fulfilled | CI Identification Process | §5.3 + Appendix A | The selection-criteria step screens every candidate against criterion (b) (failure could cause serious injury / loss of life / loss of primary capability), and the rules make safety-critical items presumptive CIs with System Safety concurrence required to omit. Floor ID F01 is explicitly tagged in the section text and carried on the Appendix A checklist row. This is the barrier B1 requirement in full.
F02 | 1. Hazard ID & Critical-Item Recognition | 3.3.1.2(1) | Classify every engineering change as Major (Class I) or Minor (Class II) | B2 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Classifying every engineering change as Major (Class I) or Minor (Class II) is the core act of the change-management function (§3.3.1.2). None of the three generated documents performs change classification; the CM plan names CCB functions as a planning factor but does not classify changes. This is the entry point of the entire change-discipline cluster and is the single most consequential gap.
F03 | 1. Hazard ID & Critical-Item Recognition | 3.3.1.2(2)(e)(6)(a) | Treat changes affecting safety as Major (Class I) | B2 | Partial | CM Planning & Management Process → Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | §5.2.2 (interface only) | The planning document requires that safety-critical CHANGES route to System Safety review via the SMS coordination interface (§5.2.2), which anticipates this requirement — but the operative rule (a change affecting safety SHALL be treated as Major/Class I) is a change-classification act that belongs to the change process. Coverage is directional, not performing.
F04 | 1. Hazard ID & Critical-Item Recognition | 3.3(3) | Support a joint Acquirer/Supplier Configuration Control Board | B2 | Partial | CM Planning & Management Process → Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | §5.2.1 factor (g) | The CMP planning factors require documenting CCB functions, responsibility, and authority (factor g), so a joint Acquirer/Supplier CCB is PLANNED for. But no generated process defines how the CCB convenes, dispositions, or records — that is change-management operation. Planned, not performed.
F05 | 1. Hazard ID & Critical-Item Recognition | 3.3.1.8.1(1) | Obtain Acquirer concurrence on Minor (Class II) classification | B2 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Obtaining Acquirer concurrence on Minor (Class II) classification is a change-processing step downstream of classification (F02). With classification itself unwritten, its concurrence sub-step is necessarily uncovered.
F06 | 2. Change Discipline & Impact Assessment | 3.3(1) | Apply configuration control to each CI, its components, and its documentation | B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Applying configuration control to each CI, its components, and its documentation is the foundational change-control obligation (§3.3(1)). The generated documents establish what to control (CIs, baselines, interfaces) but not the change-control process that governs modifications to it.
F07 | 2. Change Discipline & Impact Assessment | 3.3(2)(c) | Document, evaluate, disposition, record in CSA, and report changes and variances | B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN / Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | — | Document–evaluate–disposition–record-in-CSA–report is the end-to-end change/variance workflow, split across the change process (document/evaluate/disposition) and status accounting (record/report). Neither is written; the audit process consumes the resulting records but does not produce them.
F08 | 2. Change Discipline & Impact Assessment | 3.3(2)(e) | Incorporate approved changes into all product configuration information and implement them | B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Incorporating approved changes into all product configuration information and implementing them is change-implementation (§3.3(2)(e)). The audit process VERIFIES incorporation by sampling (a downstream check), but performing the incorporation is change-management work.
F09 | 2. Change Discipline & Impact Assessment | 3.3(2)(f) | Verify approved changes were incorporated | B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN (audit samples) | — | Verifying approved changes were incorporated (§3.3(2)(f)) is performed continuously by the change/CSA reconciliation. The audit process validates that machinery on designated items, but the continuous verification obligation itself sits in the unwritten functions — the audit is a sample, not the control.
F10 | 2. Change Discipline & Impact Assessment | 3.3.1(1) | Use an ECP to document baseline changes and submit to the change approval authority | B2, B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Using an ECP to document baseline changes and submitting it to the approval authority (§3.3.1) is the definitional ECP requirement of the change process. Not addressed in any generated document.
F11 | 2. Change Discipline & Impact Assessment | 3.3.1.1(1)(a) | Define the need for each change | B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Defining the need for each change (§3.3.1.1(1)(a)) is ECP content discipline — change-management. Uncovered.
F12 | 2. Change Discipline & Impact Assessment | 3.3.1.1(1)(e) | Incorporate the approved ECP into the configuration documentation | B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Incorporating the approved ECP into the configuration documentation (§3.3.1.1(1)(e)) is change implementation. Uncovered (the identification process defines the documentation; it does not process changes to it).
F13 | 2. Change Discipline & Impact Assessment | 3.3.1.1(1)(f) | Implement and update documentation via a documented engineering release system | B3 | Partial | CM Planning & Management Process → Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | §5.2.1 factor (h) | The CMP planning factors require establishing a documented engineering release system (factor h), so the release system is PLANNED. But implementing-and-updating documentation THROUGH that release system on each change (§3.3.1.1(1)(f)) is the change/release operation, which is not performed by any generated process. Planned, not performed.
F14 | 2. Change Discipline & Impact Assessment | 3.3.1.1(1)(g) | Record all changes in the CSA system | B3 | Not fulfilled | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | — | Recording all changes in the CSA system (§3.3.1.1(1)(g)) is a status-accounting act. The planning document lists CSA activities as a CMP factor, but the performing CSA process is not written.
F15 | 2. Change Discipline & Impact Assessment | 3.3.1.1(1)(h) | Verify the approved change was implemented correctly | B3 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Verifying the approved change was implemented correctly (§3.3.1.1(1)(h)) is change-implementation verification. Distinct from the audit's sampling validation; uncovered as a continuous control.
F16 | 2. Change Discipline & Impact Assessment | 3.3.1.4(1) | Support each ECP with data to evaluate the change and its full impacts | B4 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Supporting each ECP with data to evaluate the change and its full impacts (§3.3.1.4(1)) is impact-assessment discipline within the change process. Notably, the SUB-SUPPLIER flowdown matrix cites this as a supplier deliverable (S-04), but the prime's own performing process is unwritten.
F17 | 2. Change Discipline & Impact Assessment | 3.3.1.4(3) | Include a summary of testing validating new concepts or technology | B4 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Including a summary of testing that validates new concepts/technology in the ECP (§3.3.1.4(3)) is ECP content — change-management. Uncovered at the prime level (again flowed to suppliers via S-04, but that is flowdown, not self-performance).
F18 | 2. Change Discipline & Impact Assessment | 3.3.2(1) | Obtain Acquirer approval for any non-conforming item via a Request for Variance | B5 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Obtaining Acquirer approval for a non-conforming item via a Request for Variance (§3.3.2(1)) is the variance-control function of the change process. Uncovered (flowed to suppliers as S-05, but not self-performed).
F19 | 2. Change Discipline & Impact Assessment | 3.3.2(2) | Submit an ECP when a variance is determined permanently acceptable (recurring-to-permanent) | B5 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Submitting an ECP when a variance becomes permanently acceptable (recurring-to-permanent, §3.3.2(2)) is a core variance-discipline rule. Uncovered.
F20 | 2. Change Discipline & Impact Assessment | 3.3.1.1(1)(c) | Prepare an ECP, NOR, and supporting technical data for the change | B6 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Preparing an ECP, NOR, and supporting technical data (§3.3.1.1(1)(c)) is change-package preparation. Uncovered.
F21 | 2. Change Discipline & Impact Assessment | 3.3.4(1) | Submit a NOR for each document affected by an ECP | B6 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Submitting a NOR for each document affected by an ECP (§3.3.4(1)) is change-processing. Uncovered.
F22 | 2. Change Discipline & Impact Assessment | 3.3.4(2) | Provide all information needed to disposition each NOR | B6 | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | — | Providing all information needed to disposition each NOR (§3.3.4(2)) is change-processing. Uncovered.
F23 | 2. Change Discipline & Impact Assessment | 3.2.3.3(1) | Create a new revision of approved documentation after change approval, with before/after traceability | B7 | Partial | CM Planning & Management Process → Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | §5.2.1 factor (h), §5.4 | Creating a new revision of approved documentation after change approval WITH before/after traceability (§3.2.3.3(1)) depends on the release system the CMP plans (factor h) and the procedure-consistency discipline (§5.4). The mechanism is planned and the release process named, but the revision-on-change act is performed by the change/release process, which is unwritten. Borderline — counted Partial.
F24 | 3. As-Designed to As-Built Reconciliation | 3.4(1) | Maintain CSA legitimacy by storing valid data | B8 | Not fulfilled | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | — | Maintaining CSA legitimacy by storing valid data (§3.4(1)) is the foundational status-accounting obligation. The CMP plans CSA (§5.9) and the audit intro references the continuous CSA machinery, but no process performs status accounting.
F25 | 3. As-Designed to As-Built Reconciliation | 3.4.1(2) | Capture, store, and maintain product configuration information | B8 | Partial | CM Planning & Management Process + Configuration Audit Process (FCA/PCA) → Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | P3 §5.9; P2 §5 intro | Capturing, storing, and maintaining product configuration information (§3.4.1(2)) is planned by the CMP information-processes section (§5.9) and referenced by the audit process as the at-scale machinery the audits validate (F25 tagged in the audit §5 intro). But the performing status-accounting process is unwritten, so the capture/store/maintain act itself is not fulfilled by a Level III process. Referenced, not performed.
F26 | 3. As-Designed to As-Built Reconciliation | 3.4.1(3)(a) | Capture and maintain currently approved configuration information by each CI's identification number | B8, B11 | Not fulfilled | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | — | Maintaining currently approved configuration information BY each CI's identification number (§3.4.1(3)(a)) is status accounting. The identification process ASSIGNS the identifiers (§5.7) and the CI index template is keyed by them, but keeping current-configuration status against them over time is the CSA function — unwritten. The template exists; the process that maintains it does not.
F27 | 3. As-Designed to As-Built Reconciliation | 3.4.1(3)(c) | Store and manage all product configuration information | B8 | Partial | CM Planning & Management Process → Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | §5.9 | Storing and managing all product configuration information (§3.4.1(3)(c)) is planned as a CMP information process (§5.9) but performed by status accounting. Planned, not performed.
F28 | 3. As-Designed to As-Built Reconciliation | 3.4.1(4)(c) | Secure, safeguard, and retrieve recorded configuration information | B8 | Partial | CM Planning & Management Process → Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | §5.9, §6 | Securing, safeguarding, and retrieving recorded configuration information (§3.4.1(4)(c)) is required as a CMP planning factor (§5.9) and the contract-completion data delivery (§6 records), so it is planned. The performing process (CSA retention/retrieval) is unwritten. Planned, not performed.
F29 | 3. As-Designed to As-Built Reconciliation | 3.5.3(1) | Conduct the PCA to verify product configuration documentation is consistent with the validated CI | B9 | Fulfilled | Configuration Audit Process (FCA/PCA) | §5.4 | Conducting the PCA to verify product configuration documentation is consistent with the validated CI (§3.5.3(1)) is the core PCA objective and is performed in §5.4, with F29 explicitly tagged in the §5 intro. Barrier B9 in full.
F30 | 3. As-Designed to As-Built Reconciliation | 3.5.3(2) | Confirm the CI against the PPSL and verify proper parts are installed | B9 | Fulfilled | Configuration Audit Process (FCA/PCA) | §5.4.3 | Confirming the CI against the PPSL and verifying proper parts are installed (§3.5.3(2)) is a PCA hardware conduct step, tagged F30 in §5.4.3. Fulfilled.
F31 | 3. As-Designed to As-Built Reconciliation | 3.5.3(4) | Document each PCA non-compliance and provide it to the Acquirer | B9 | Fulfilled | Configuration Audit Process (FCA/PCA) | §5.4.5 | Documenting each PCA non-compliance and providing it to the Acquirer (§3.5.3(4)) is performed in the PCA results step, tagged F31. Fulfilled.
F32 | 3. As-Designed to As-Built Reconciliation | 3.4.1(3)(b) | Capture and maintain all historical configuration information with traceability from contract award to present | B10 | Partial | Configuration Audit Process (FCA/PCA) → Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | §5 intro | Capturing and maintaining ALL historical configuration information with traceability from contract award to present (§3.4.1(3)(b)) is referenced by the audit §5 intro as CSA machinery (F32 tagged there) but performed by status accounting. Referenced, not performed.
F33 | 3. As-Designed to As-Built Reconciliation | 3.4.1(6) | Document the incorporation of all retrofit changes to units identified for retrofit | B11 | Partial | Configuration Audit Process (FCA/PCA) → Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | §5 intro; §5.4.3 | Documenting the incorporation of retrofit changes to units identified for retrofit (§3.4.1(6)) is referenced by the audit process (F33 tagged, and the PCA examines change incorporation) but the retrofit-record maintenance is a CSA/change function — unwritten. Referenced, not performed.
F34 | 3. As-Designed to As-Built Reconciliation | 3.5.3.1(1)(b) | Identify differences between the production CI and the development CI used for FCA | B12 | Fulfilled | Configuration Audit Process (FCA/PCA) | §5.4.3 | Identifying differences between the production CI and the development (FCA) CI (§3.5.3.1(1)(b)) is a PCA conduct step, tagged F34, with the certification-that-differences-do-not-degrade requirement carried in the exit criteria. Fulfilled.
F35 | 4. Supply Chain, Interfaces & Verification | 3.2.5.1(1) | Identify internal and external interface requirements | B13 | Fulfilled | CI Identification Process | §5.5 / §5.5.1 | Identifying internal and external interface requirements (§3.2.5.1(1)) is assigned to Systems Engineering with CM recording it in the interface register (§5.5.1), F35 tagged. Note: the generated doc correctly scopes CM to VERIFY/RECORD while SE identifies — the floor obligation on the company is met. Fulfilled.
F36 | 4. Supply Chain, Interfaces & Verification | 3.2.5.1(2) | Incorporate interface information into the FCD/ACD/PCD | B13 | Fulfilled | CI Identification Process | §5.8 | Incorporating interface information into the FCD/ACD/PCD (§3.2.5.1(2)) is performed in the configuration documentation determination step, F36 tagged. Fulfilled.
F37 | 4. Supply Chain, Interfaces & Verification | 3.2.5.1(3) | Maintain configuration control of baselined interface requirements | B13 | Fulfilled | CI Identification Process | §5.9 | Maintaining configuration control of baselined interface requirements (§3.2.5.1(3)) is performed in the baseline establishment step, F37 tagged, with baselined-interface changes routed to formal change action. Fulfilled.
F38 | 4. Supply Chain, Interfaces & Verification | 3.2.5.2(1) | Provide a representative to the Acquirer's ICWG where one exists | B13 | Fulfilled | CI Identification Process | §5.5.3 | Providing a representative to the Acquirer's ICWG where one exists (§3.2.5.2(1)) is performed in the interface documentation control step, F38 tagged, correctly marked conditional on ICWG existence. Fulfilled.
F39 | 4. Supply Chain, Interfaces & Verification | 3.4.1(3)(j) | Record and report sub-tier supplier data with traceability to the next higher assembly | B14 | Fulfilled | CM Planning & Management Process | §5.8 | Recording and reporting sub-tier supplier data with traceability to the next higher assembly (§3.4.1(3)(j)) is performed in the supply-chain CM step, F39 tagged, and reinforced by the flowdown matrix (R-10 / traceability record) and effectiveness workbook. Fulfilled.
F40 | 4. Supply Chain, Interfaces & Verification | 3.(2) | Require sub-suppliers to comply with or suitably tailor the same CM requirements imposed on the Supplier | B15 | Fulfilled | CM Planning & Management Process | §5.8 | Requiring sub-suppliers to comply with or suitably tailor the same CM requirements (§3.(2)) is performed in the supply-chain CM step, F40 tagged, and fully operationalized by the flowdown matrix, guide, and classification log (the recorded work-type classification is the tailoring rationale). Fulfilled and the best-supported requirement in the set.
F41 | 4. Supply Chain, Interfaces & Verification | 3.(4) | Support Acquirer audits of Supplier and sub-supplier CM | B15 | Fulfilled | CM Planning & Management Process | §5.7–5.8 | Supporting Acquirer audits of Supplier and sub-supplier CM (§3.(4)) is performed via the periodic-assessment (§5.7) and supply-chain (§5.8) steps, F41 tagged. Fulfilled.
F42 | 4. Supply Chain, Interfaces & Verification | 3.5.2(2) | Conduct the FCA to verify the CI meets performance requirements per approved FCD/ACD | B16 | Fulfilled | Configuration Audit Process (FCA/PCA) | §5.3 | Conducting the FCA to verify the CI meets performance requirements per approved FCD/ACD (§3.5.2(2)) is the core FCA objective, performed in §5.3, F42 tagged. Fulfilled.
F43 | 4. Supply Chain, Interfaces & Verification | 3.5.2(3) | Document each FCA non-compliance and provide it to the Acquirer | B16 | Fulfilled | Configuration Audit Process (FCA/PCA) | §5.3.4 | Documenting each FCA non-compliance and providing it to the Acquirer (§3.5.2(3)) is performed in the FCA results step, F43 tagged. Fulfilled.
F44 | 4. Supply Chain, Interfaces & Verification | 3.5.2.1(1)(c) | Provide a requirements-to-test traceability matrix (each requirement maps to a test step) | B16 | Fulfilled | Configuration Audit Process (FCA/PCA) | §5.3.2 | Providing a requirements-to-test traceability matrix (§3.5.2.1(1)(c)) is performed as a pre-audit submittal that becomes part of the FCA minutes, F44 tagged, and is the anchor exercise of the audit training course. Fulfilled.

## Open Gaps
Floor ID | Clause | Requirement | Status | Owning (unwritten) process | What is needed to close
F02 | 3.3.1.2(1) | Classify every engineering change as Major (Class I) or Minor (Class II) | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F03 | 3.3.1.2(2)(e)(6)(a) | Treat changes affecting safety as Major (Class I) | Partial | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F04 | 3.3(3) | Support a joint Acquirer/Supplier Configuration Control Board | Partial | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F05 | 3.3.1.8.1(1) | Obtain Acquirer concurrence on Minor (Class II) classification | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F06 | 3.3(1) | Apply configuration control to each CI, its components, and its documentation | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F07 | 3.3(2)(c) | Document, evaluate, disposition, record in CSA, and report changes and variances | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F08 | 3.3(2)(e) | Incorporate approved changes into all product configuration information and implement them | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F09 | 3.3(2)(f) | Verify approved changes were incorporated | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F10 | 3.3.1(1) | Use an ECP to document baseline changes and submit to the change approval authority | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F11 | 3.3.1.1(1)(a) | Define the need for each change | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F12 | 3.3.1.1(1)(e) | Incorporate the approved ECP into the configuration documentation | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F13 | 3.3.1.1(1)(f) | Implement and update documentation via a documented engineering release system | Partial | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F14 | 3.3.1.1(1)(g) | Record all changes in the CSA system | Not fulfilled | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.
F15 | 3.3.1.1(1)(h) | Verify the approved change was implemented correctly | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F16 | 3.3.1.4(1) | Support each ECP with data to evaluate the change and its full impacts | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F17 | 3.3.1.4(3) | Include a summary of testing validating new concepts or technology | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F18 | 3.3.2(1) | Obtain Acquirer approval for any non-conforming item via a Request for Variance | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F19 | 3.3.2(2) | Submit an ECP when a variance is determined permanently acceptable (recurring-to-permanent) | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F20 | 3.3.1.1(1)(c) | Prepare an ECP, NOR, and supporting technical data for the change | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F21 | 3.3.4(1) | Submit a NOR for each document affected by an ECP | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F22 | 3.3.4(2) | Provide all information needed to disposition each NOR | Not fulfilled | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F23 | 3.2.3.3(1) | Create a new revision of approved documentation after change approval, with before/after traceability | Partial | Change Management process (EIA-649-1A §3.3) — NOT YET WRITTEN | Write the change management Level III process: change classification (Major/Minor), ECP/variance workflow, impact assessment, CCB operation, incorporation and verification.
F24 | 3.4(1) | Maintain CSA legitimacy by storing valid data | Not fulfilled | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.
F25 | 3.4.1(2) | Capture, store, and maintain product configuration information | Partial | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.
F26 | 3.4.1(3)(a) | Capture and maintain currently approved configuration information by each CI's identification number | Not fulfilled | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.
F27 | 3.4.1(3)(c) | Store and manage all product configuration information | Partial | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.
F28 | 3.4.1(4)(c) | Secure, safeguard, and retrieve recorded configuration information | Partial | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.
F32 | 3.4.1(3)(b) | Capture and maintain all historical configuration information with traceability from contract award to present | Partial | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.
F33 | 3.4.1(6) | Document the incorporation of all retrofit changes to units identified for retrofit | Partial | Status Accounting process (EIA-649-1A §3.4) — NOT YET WRITTEN | Write the status accounting Level III process: capture/store/maintain configuration records by CI ID, historical traceability, secure retention and retrieval, change and variance recording/reporting.