## Instructions
Sub-Supplier CM Effectiveness Workbook — Template
Implements [XXX-CM-PROC-003] §5.8 and Floor ID F40: the methods used to determine sub-supplier CM process effectiveness and the actions taken when a process is determined ineffective. Companion to the Sub-Supplier CM Flowdown Matrix (which defines what was imposed per supplier — the evaluation basis) and [XXX-CM-GUIDE-002].
Operating model — continuous accrual, judgment roll-up
• Evidence accrues transaction by transaction: log every SDRL submittal on the 'SDRL Receipt Log' as it arrives and score it at review (first-pass accepted / accepted with comment / rejected, with defect codes). Log non-submittal events (escapes, unauthorized changes, traceability gaps, audit findings) on the 'Findings & Escapes Log' as they occur.
• The 'Supplier Evaluation Record' rolls the logs up by supplier ID via formulas (submittal counts, first-pass rate, open findings, escape count) and holds the judgment fields: the determination, rationale, actions, and sign-offs. Formula cells are shaded — do not overwrite.
• Determinations are refreshed on a tiered cadence as a backstop (WT4/WT6 annual; WT1/WT2/WT7 annual–biennial per risk; WT5/WT8 event-driven) AND on trigger events: rejection streak, any escape classified safety-relevant, ineffective reconciliation evidence, audit finding, or a change relevant to [XXX-CM-PROC-002] Appendix C items C3–C5.
Determination scale and actions (F40)
• Effective: imposed requirements are being met; routine surveillance continues.
• Conditionally effective: deficiencies with credible correction underway; actions ladder — increased surveillance, corrective action request (CAR), source inspection, elevated SDRL review.
• Ineffective: systemic failure to meet imposed requirements; actions ladder — CAR with executive engagement, source inspection/witness points, payment/delivery holds per contracts, new-award hold, and where warranted disqualification. Record all actions on the 'Actions Log' and track to closure.
Outbound linkages
• An Ineffective (or safety-relevant Conditionally effective) determination: (1) triggers re-run of the [XXX-CM-PROC-002] Appendix C audit-designation assessment for CIs this supplier builds (items C4/C5/C7); (2) is reported as SM-0001 safety data where safety-relevant (subcontractor disclosures, work not per approved data); (3) triggers review of any CM floor equivalent control that relies on this supplier's process (program CM Floor Compliance Matrix).
• The Dashboard computes portfolio status by formula. Enter all dates as date values, not text.

## Evaluation Criteria
Criterion ID | Evidence Stream | What Effective Looks Like | Source | Applies To (Work Types)
E-01 | CM plan adequacy (S-01) | Plan accepted; implements the imposed requirement set including recursive sub-tier flowdown; kept current through revisions. | SDRL Receipt Log (S-01) | WT2–WT4, WT6, WT7
E-02 | Reconciliation process capability (S-02) | Documented as-designed/as-built (or as-maintained) reconciliation process accepted; method covers all deliverable configurations at scale. | SDRL Receipt Log (S-02) | WT1, WT2, WT4, WT6, WT7
E-03 | Reconciliation report quality (S-08) | Reports delivered per delivery/lot; deltas dispositioned, none aged past threshold; content expressed in PTR identifiers; zero deltas discovered by company receiving that the report missed. | SDRL Receipt Log (S-08) + Findings Log | WT1, WT2, WT4, WT6, WT7
E-04 | Part traceability completeness (S-06) | PTRs complete on first pass: serials, lot/batch, life-limited designation with limits and life consumed, safety-critical and special-handling designations, NHA traceability (F39). Designation authorship per work type honored. | SDRL Receipt Log (S-06) | WT1, WT2, WT4, WT5, WT6, WT7
E-05 | Change control discipline (S-04) | ECPs complete with need, impact data, and NORs on first pass; no baseline-affecting change implemented without approval; safety-affecting changes flagged Class I. | SDRL Receipt Log (S-04) + Findings Log | WT2–WT4, WT6, WT7
E-06 | Variance discipline (S-05) | Departures RFV'd before delivery; zero post-delivery discoveries of departures that should have been RFV'd (the key escape signal); recurring variances converted to ECP (F19). | SDRL Receipt Log (S-05) + Findings Log | All build/process types
E-07 | Process change notification (S-03) | No unauthorized change to frozen/approved processes; notifications timely per SSOW notice period. | SDRL Receipt Log (S-03) + Findings Log | WT8; others where flagged
E-08 | CSA records currency (S-07) | CSA reports timely, current, historical traceability intact, retrievable per data terms. | SDRL Receipt Log (S-07) | WT2, WT4, WT6; tailored others
E-09 | Audit performance (S-10–S-12) | Where designated: audits conducted/supported per role; substance in full; action items closed by suspense. | SDRL Receipt Log + Actions Log | Per designation and role
E-10 | CM process audit findings (F41) | Company/Acquirer CM-system audit findings closed by suspense; no repeat findings. | Findings Log + Actions Log | All except WT5

## SDRL Receipt Log
Entry ID | Supplier ID | Supplier Name | SSOW/PO | SDRL ID | Submittal Description | Received Date | Review Due | Reviewed Date | Review Result | Defect Code(s) | Criterion (E-xx) | Reviewer | Notes
SR-0001 | SUP-014 | ACME Actuation | SSOW-114 | S-08 | Recon report, lot 7 | 2026-06-20 | 2026-07-05 | 2026-06-28 | Accepted first-pass |  | E-03 | [name] | Example row — replace
SR-0002 | SUP-014 | ACME Actuation | SSOW-114 | S-06 | PTR, lot 7 | 2026-06-20 | 2026-07-05 | 2026-06-30 | Rejected | D3 (life consumed missing) | E-04 | [name] | Example row — replace

## Findings & Escapes Log
Finding ID | Supplier ID | Supplier Name | SSOW/PO | Date | Finding Type | Description | Safety-Relevant (Y/N) | SM-0001 Report Ref (if Y) | Criterion (E-xx) | Action ID(s) | Status | Notes
FE-0001 | SUP-014 | ACME Actuation | SSOW-114 | 2026-07-02 | Post-delivery departure (should have been RFV'd) | Undocumented shim substitution found at receiving, lot 6 | Y | SDR-2026-041 | E-06 | AC-0001 | Open | Example row — replace

## Supplier Evaluation Record
Supplier ID | Supplier Name | SSOW/PO(s) | Work Type(s) | Cadence | Submittals Logged | First-Pass Accepted | Rejected | First-Pass Rate | Open Findings | Safety-Relevant Findings | Open Actions | Determination | Determination Date | Next Determination Due | Rationale / Triggering Evidence | App C Re-run Triggered (Y/N + ref) | CM Sign-off (name/date) | Notes
SUP-014 | ACME Actuation | SSOW-114 | WT2 | Annual | 2 | 1 | 1 | 50% | 1 | 1 | 1 | Not yet determined | [5 empty] | Example row — replace IDs; formulas roll up automatically

## Actions Log
Action ID | Supplier ID | Supplier Name | Source (Finding/Determination ref) | Action Type | Description | Owner | Due Date | Status | Closed Date | Closure Evidence | Notes
AC-0001 | SUP-014 | ACME Actuation | FE-0001 | CAR + source inspection | CAR issued for RFV process failure; source inspection at next 3 lots | [name] | 2026-08-15 | Open |  |  | Example row — replace

## Dashboard
Sub-Supplier CM Effectiveness Dashboard
Formula-driven — do not overwrite column B. Reporting date drives overdue counts.
Reporting date: | 2026-07-18
Suppliers under evaluation | 1
Determination — Effective | 0
Determination — Conditionally effective | 0
Determination — Ineffective | 0
Not yet determined | 1
Determinations overdue (Next Due < reporting date) | 0
Open + in-work findings (all suppliers) | 1
Safety-relevant findings (all suppliers) | 1
Open/overdue actions (all suppliers) | 1
SDRL submittals logged (all suppliers) | 2
Portfolio first-pass acceptance rate | 50%

## Lists
Defect Codes | Determination | Finding Type | Safety-Relevant | Action Status | Cadence
D1 — Content incomplete | Effective | Post-delivery departure (should have been RFV'd) | Y | Open | Annual
D2 — Wrong/rev data used | Conditionally effective | Unauthorized process change | N | In work | Biennial
D3 — Traceability/PTR gap | Ineffective | Traceability gap discovered |  | Closed | Event-driven
D4 — Late submittal | Not yet determined | Unincorporated/undocumented change |  | Overdue
D5 — Format/DID non-compliance |  | CM process audit finding
D6 — Unresolved prior comment |  | Reconciliation miss (delta found by company)
Late/withheld disclosure
Other